## Sheet1
Dept/ Module | Seq # | Company | Task Name | Description | Day of the Week | Due Date | Status | J | Comments FY21 | Comments FY22 | Comments FY23
Financial Accounting |  | GT | POOELS Report for managing non-sponsored PY PO's - Posted to Controller's Office website | POOELS Report (for managing non-sponsored PY PO's) Purchase Order Obligation and Expense Summary Report – GTCR posted to Controller’s Office website on Monday's. Posted weekly through closeout. | Tuesday | 2023-03-07 | Ongoing | Christopher Drummond Amry Stanley Tyler Dixon | Monthly through April, Weekly beginning in May
Procurement |  | GT | Deadline – PO items requiring formal bidding ($25K or greater) | Deadline – PO items requiring formal bidding ($25K or greater) | Friday | 2023-03-10 | Complete | Erin Mitchell
Financial Accounting |  | GT/ATHL | Year End Town Hall Meeting | Discuss Close Out Letter and Chronological Schedule | Tuesday | 2023-03-21 | Complete | Christopher Drummond Amry Stanley
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-04-14 | Complete | David Adcock | Friday - Saturday
ERP |  | GT/ATHL | Monthly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 9AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-04-14 | Complete | David Adcock | Friday - Saturday
Procurement |  | GT | Deadline – PO items requiring sole source justification approval from the State ($500K or greater) | Deadline – PO items requiring sole source justification approval from the State ($500K or greater) | Friday | 2023-04-14 | Complete | Erin Mitchell
Budgets |  | GT | Deadline - Carry Forward Requests for Gen Ops | Deadline – Carry forward requests for Gen Ops submitted to Budget Office | Tuesday | 2023-04-18 | Complete | Isabel Lynch Lisa Godfrey
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-04-21 | Complete | David Adcock | Friday - Saturday
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-04-28 | Complete | David Adcock | Friday - Saturday
Procurement |  | GT | Deadline – PO items requiring sole source documentation ($10,000 or greater) | Deadline – PO items requiring sole source documentation (not subject to the deadline above) – ($25,000 or greater) | Friday | 2023-04-28 | Complete | Erin Mitchell
Financial Accounting |  | GT/ATHL | Refresh "gatech7" Tenant for Closeout Testing | Refresh "gatech7" tenant to facilitate closeout testing | Monday | 2023-05-01 | Complete | Nate Watkins Chhaya Amin Michael McCoy Marvin Petty Antinina Wilkerson Yongmei Zhang Timothy Hughes |  |  | 5/5/23 - EADI: Waiting on Security
ERP |  | GT/ATHL | Quarterly Planned Maintenance ***Sandbox, Sandbox Preview and Impl | Tenant downtime - Friday 9 PM to Saturday 1 PM Eastern time | Friday | 2023-05-05 | Complete | David Adcock | Friday - Saturday
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-05-05 | Complete | David Adcock | Friday - Saturday
Financial Accounting |  | GT | Add New Fiscal Year (FY24) in Workday | Create new Fiscal Year (FY24) in Workday | Friday | 2023-05-05 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-05-12 | Complete | David Adcock | Friday - Saturday
Procurement |  | GT | PO Deadline - Commodity/Service on State/GT Contract | Deadline – PO items for any Commodity/Service on State/GT Contract – ($25,000 or greater) | Friday | 2023-05-12 | Complete | Whitney Tate Erin Mitchell
Procurement |  | GT | Open Obligation (Encumbrance) Reports for Mass Closures due via ServiceNow Ticket | Open Obligation (Encumbrance) Reports for mass Closures due via ServiceNow Ticket - PO’s issued prior to March 1, 2023 | Friday | 2023-05-12 | Complete | Whitney Tate Erin Mitchell
SupplAccts |  | GT/ATHL | Supplier registration deadline | Deadline to submit new supplier registration through the Supplier Portal for FY23 | Friday | 2023-05-12 | Complete | Laura Jamison Daniel Stewart
Payroll |  | GT | MSS Transactions due for non-faculty Summer Semester Appointments | Manager Self-Service transactions due for non-faculty (Graduate Students, Post Docs, etc.) summer semester appointments | Tuesday | 2023-05-16 | Complete | Jerri Phillips
Financial Accounting |  | GT/ATHL | Year-End Task Closeout Review Meeting | Review and discuss Year-End Task List with those assigned to tasks. | Wednesday | 2023-05-17 | Complete | Serena Simpson Yongmei Zhang Tyler Dixon Amy Herron |  | Amy Herron Comment: Per discussion with Carol this item was the meeting we used to have pre-Covid and pre-Workday with all parties to discuss the task list. This meeting used to be in person, usually at Procurement & Business Services. We've been having the weekly year-end meetings since Covid and Workday so the big meeting is not necessary.
Financial Accounting |  | GT | Send reminder to Campus Service Centers regarding FY2023 Billing Due Dates | Reference Closeout Memo. Service Centers need to bill at least through May 2023 | Wednesday | 2023-05-17 | Complete | Christopher Drummond Amry Stanley | Working on updating contact list; hoping to send out by 5/23
Financial Accounting |  | GT | PYPO/SURPLUS - Review Purchase Order Negative Balances for Prior Year PO's and create EIB loads to Correct | Review Purchase Order Negative Balances for Prior Year PO's and create EIB loads to Correct | Wednesday | 2023-05-17 | Ongoing | Christopher Drummond Amry Stanley | POOELS Report is reviewed and any necessary EIBs are loaded on a weekly basis until year end.
Financial Accounting |  | GT/ATHL | Meet to discuss YE Integration Schedule | Meet to discuss YE EDW Integration Schedule | Thursday | 2023-05-18 | Ongoing | Chhaya Amin Michael McCoy Vishnu Kothuru Serena Simpson Yongmei Zhang Tyler Dixon Timothy Hughes |  | Follow-up meeting next week with Payroll and FinOps to finalize key integration schedule. (5/25/2023)
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-05-19 | Complete | David Adcock | Friday - Saturday
Procurement |  | GT | Deadline for PO's from $2,500-$9,999 | Deadline – PO items not requiring bids but require Purchasing Review ($2,500 - $24,999) | Friday | 2023-05-19 | Complete | Whitney Tate Erin Mitchell
ERP |  | GT/ATHL | Quarterly Planned Maintenance - PROD | Tenant downtime: Saturday 2 AM to Saturday 1 PM Eastern Time | Saturday | 2023-05-20 | Complete | David Adcock
Payroll |  | GT | Summer Pay Deadline | Deadline to enter Summer Pay for May pay date. Information entered after this date will be transferred to oneUSG Connect after go-live. | Monday | 2023-05-22 | Complete | Jerri Phillips
Payroll |  | GT | Summer Pay Deadline | Summer pay panels in OneUSG Connect closed | Monday | 2023-05-22 | Complete | Jerri Phillips
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-05-26 | Complete | David Adcock | Friday - Saturday
Procurement |  | GT | Deadline - Change Order Requisitions for PO Adjustments | Deadline for BR23/BR22/BR21/BR20/BR19 Change Order Requisitions (submitted & approved) | Friday | 2023-05-26 | Complete | Steve Smith Whitney Tate
Budgets |  | GT | Deadline - Carry Forward Request Revisions for Gen Ops | Revisions to Gen Ops carry forward requests due to Budget Office | Wednesday | 2023-05-31 | Complete | Isabel Lynch Lisa Godfrey
Financial Accounting |  | GT | Deadline - Nuclear Magnetic Resonance Journals | Deadline Nuclear Magnetic Resonance year-end transactions | Friday | 2023-06-02 | Complete | Monika Nasir |  |  | Monika Nasir replaced Julia Thomas - Per Julia 06.06.2023
Payroll |  | GT | MSS Transactions Due for Biweekly Pay Period Ending 6/11/23 | Manager Self-Service (MSS) transactions for employee payroll actions due - Biweekly pay period ending 6/11 | Monday | 2023-06-05 | Complete | Jerri Phillips
Payroll |  | GT | OneBudget system open for Final FY23 Budget Amendments | oneBudget system open for final FY23 budget amendments | Monday | 2023-06-05 | Complete | Jamie Fernandes |  | Jamie: Notified campus the June BA is open as of 6/6 and will close on 6/10
Budgets |  | GT | Deadline - Final oneBudget Budget Amendments | Final Budget Amendment due to Budget Office 5pm | Monday | 2023-06-05 | Complete | Jamie Fernandes Lisa Godfrey |  | 6/17 - Per Lisa - We anticipate posting to WD around Wednesday June 22nd. | Per Richard Tanner, this is complete and closed for campus. Some BA will post to WD later this month.
Financial Accounting | YE2 | GT/ATHL | Add Year-End Closeout Message to Workday | Certain Workday Business Processes will be unavailable starting at 5pm on Friday, June 16th until 9am on Tuesday, July 5th to facilitate year-end closeout. Click here for details by area. Link for "Click here": www.controller.gatech.edu/monthyear-end. | Wednesday | 2023-06-07 | Complete | Chhaya Amin Yongmei Zhang Tyler Dixon Serena Simpson | WKDAY-5714 | WKDAY-6811 | Create a jira similar to our month-end message to request this year end message on workday. (also a sub-jira on displaying this announcement at top of page) - create Jira about 2 weeks prior (wkday-8543)
Financial Accounting | YE1 | GT/ATHL | Add Year-End Closeout Message to Techworks (done in IT service now portal) | Certain Workday Business Processes will be unavailable starting at 5pm on Friday, June 16th until 9am on Wednesday, July 5th to facilitate year-end closeout. Click here for details by area. Link for "Click here": www.controller.gatech.edu/monthyear-end. Going forward, please submit a request in the IT Service Now portal to David Lacy (IT Service Delivery Manager) | Wednesday | 2023-06-07 | Complete | Chhaya Amin Ambica Letkeman John Gisi Yongmei Zhang Tyler Dixon Serena Simpson | WKDAY-5714 | WKDAY-6811 | Going forward, please submit a request in the IT Service Now portal to David Lacy (IT Service Delivery Manager) (wkday-8543)
Financial Accounting | YE3 | GT/ATHL | Add Jira ticket for more Workday bandwidth for intensive year-end processes. | Certain workday processes require more bandwidth, Controller's Office will be creating a Jira ticket to increase Workday bandwidth from June 22nd - June 26th and again on July 1st - July 3rd. | Wednesday | 2023-06-07 | Complete | Chhaya Amin Yongmei Zhang Tyler Dixon Serena Simpson Timothy Hughes |  |  | (wkday-8544)
ERP |  | GT/ATHL | Monthly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 9AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-06-09 | Complete | David Adcock | Friday - Saturday
Bursar/Treasury |  | GT | Deadline - Petty Cash Requests | Deadline - Petty Cash Requests | Friday | 2023-06-09 | Complete | Curlyne Andrews Leanne Scheffield Maurena Maynor
Business Assets |  | GT | Send reminder to Housing, Facilities, Student Health Pharmacy, Post Office, and Library to Perform Year-End Inventory Count | Send reminder to Housing, Facilities, Student Health Pharmacy, Post Office, and Library to Perform Year-End Inventory Count | Friday | 2023-06-09 | Complete | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur
Expenses |  | GT | Deadline for Expense Reports for FY2023 | Deadline for Expense Report submission to Expense Partners (Travel Team) to guarantee FY23 payment. Approvals must be complete and documentation must be attached. | Friday | 2023-06-09 | Complete | Laura Jamison Jennifer Jacobs
Financial Accounting |  | GT | Create Year-End System Integration Schedule | Create Year-End System Integration Schedule | Friday | 2023-06-09 | Complete | Chhaya Amin Michael McCoy Timothy Hughes Serena Simpson Yongmei Zhang Tyler Dixon |  | WKDAY-7005 | WKDAY-8516
Financial Accounting |  | GT | Deadline OHR Training EIB Journal Loads | Deadline OHR Training EIB Journal Loads | Friday | 2023-06-09 | Complete | Cedric Franklin
Financial Accounting |  | GT | Deadline Parking Office EIB or Online Journals | Deadline Parking Office EIB or Online Journals | Friday | 2023-06-09 | Complete | Cassandra Railey |  | Wayne: Sherry has been contacted waiting for response
Financial Accounting |  | GT/ATHL | Ensure Workday Book Codes are aligned to the Correct Books | CAPITAL, COMMON, GAAP, etc. | Friday | 2023-06-09 | Complete | Maurena Maynor Amy Herron |  | 6/14 - Per Amy/Maurena will circle back | Please refer to the procedure called "Workday Books Book Codes and Ledgers" saved here - K:\Year End\FY2023.
SupplAccts |  | GT | Deadline to submit supplier invoice requests (SIRs), adhoc payments, and wire transfers | Deadline to submit supplier invoice requests (SIRs), adhoc payments, and wire transfers. PO must have sufficient funds to cover payment. Change Orders must be complete. Receipts must be entered prior to this date. *“Pre-paid expense” must be noted on the Supplier Invoice Request (SIR) or invoice for FY23 expenses required to be paid prior to June 09,2023 | Friday | 2023-06-09 | Complete | Laura Jamison Whitney Tate Daniel Stewart
Security | SEC01 | GT | Supplier PORTAL CLOSED for submitting invoices for FY2023 REMOVE Access for Supplier PORTAL for submitting invoices | Supplier PORTAL CLOSED for submitting invoices for FY2023 REMOVE Access for Supplier PORTAL for submitting invoices Supplier Contract As Self on the Supplier Invoice BP (@ 5PM) | Friday | 2023-06-09 | Complete | Marvin Petty Chhaya Amin David Adcock | It is very important that this task is completed in FY22; this probably needs to be shut down the day before final AP payments
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-06-09 | Complete | David Adcock | Friday - Saturday
Payroll |  | GT | Deadline - Late Time Sheets for Pay Periods Prior to 5/13 | Deadline - Late Time Sheets for Pay Periods Prior to 5/13 | Monday | 2023-06-12 | Complete | Jerri Phillips
Payroll |  | GT | Deadline - Timesheets Due for Biweekly Pay Period Ending 6/11/22 | Timesheets for 6/10 BW Pay Period submitted & approved (including late pay periods after 5/13) | Monday | 2023-06-12 | Complete | Jerri Phillips
Procurement |  | GT | Open Obligation (Encumbrance) Reports for Mass Closures due via ServiceNow Ticket | Open Obligation (Encumbrance) Reports for Mass Closures due via ServiceNow Ticket – PO’s issued March 1, 2023 to May 31, 2023 | Monday | 2023-06-12 | Complete | Erin Mitchell Whitney Tate | 06.13.22 Send email to Ajay and Whiteney, waiting for their feedback on the status.
SupplAccts |  | GT | Review July 2023 (FY24) Rent Payments | Review July 2023 (FY24) Rent Payments and ensure payment are made in June and charged to prepaid expense | Tuesday | 2023-06-13 | Complete | Laura Jamison Daniel Stewart |  | 6/7/22: Per Abbie: Campus is still submitting some payments for July. We are processing the prepaids as they come through. Most have been completed. 6/9/22: some campus units have requested an extension for their lease payments to be sent in by June 10th. In which case I anticipate the lease payments to be completed by next check run. We can only make the payments when campus submits them. 6/13/22 - Per Abbie: All the lease payments have been reviewed. Payments will be completed during the check run tomorrow.6/14/2022 - This task completed on this day. | Completed 6/15
SupplAccts |  | GT | Review Open Credit Memos | Review Open Credit Memos | Tuesday | 2023-06-13 | Complete | Laura Jamison Daniel Stewart |  |  | Completed 6/15
Business Assets |  | GT | Finance Lease Recon - Reconcile payments for Financial Leases to lease payment schedules | Financial Lease Recon - Reconcile payments for Financial Leases to lease payment schedules | Wednesday | 2023-06-14 | Complete | Kelly MacArthur Holly Seel Amy Herron | 6/25/21 Amy: Still working on it. Anticipate completing next week 6/29/21: All Payments have been made. Working on recorded them. Should be completed before common book closes | 06/17 - Per Amy: This task should be completed this afternoon. | Pending completion of "Review July 2023 (FY24) Rent Payments" which has an ETA of Friday 6/16. Kelly stated this will be complete that Friday or Monday following. 6/20/23 - Kelly to update today.
Payroll |  | GT | Manager Self-Service (MSS) transactions due for Monthly Pay Period Ending 6/30 | Manager Self-Service (MSS) transactions due for Monthly Pay Period Ending 6/30 | Wednesday | 2023-06-14 | Complete | Jerri Phillips
Payroll |  | GT | Biweekly Pay Period End Date - Period Ending 6/10/23 | Deadline for timesheets - Biweekly pay period ending 6/10 | Wednesday | 2023-06-14 | Complete | Jerri Phillips
Payroll |  | GT | MSS transactions Due - Biweekly Pay Period Ending 6/30/23 | Manager Self-Service (MSS) transactions for employee payroll actions due - Monthly pay period ending 6/30 | Wednesday | 2023-06-14 | Complete | Jerri Phillips
Payroll |  | GT | Final Biweekly Payroll Posted to the Ledger - Period Ending 6/10 | BW payroll transactions from Pay Period Ending 6/10 posted to ledger | Wednesday | 2023-06-14 | Complete | Jerri Phillips Yongmei Zhang |  | 6/15/22 - Per Terryl this should process today. If not then Thursday 16th.
Procurement |  | GT | Deadline - POs for contracted purchases less than $25k where the cotract is selected on the requisition | Campus Deadline - POs for contracted purchases less than $25k where the cotract is selected on the requisition | Wednesday | 2023-06-14 | Complete | Erin Mitchell Whitney Tate
Financial Accounting |  | GT | Deadline - Final Off-Cycle Payroll Check Requests for FY2023 | Deadline - Final Off-Cycle Payroll Check Requests for FY2023 | Thursday | 2023-06-15 | Complete | Jerri Phillips
Financial Accounting |  | GT/ATHL | E-mail to Accountants, Cost Center Managers, Driver Worktag Managers, etc. regarding Workday availability during year end close | Send notice to campus regarding Workday down time for end close (fin-all@office365.gatech.edu; Send email to Alana DeAngeleis) | Thursday | 2023-06-15 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson | Once Jira is completed, email will be sent out |  | Created new controller's office email in order to send to fin-all group. New email is no-reply@business.gatech.edu
Financial Accounting | YE4 | GT/ATHL | Updated Grid on Controller's Office Year End Page to indicate down time for specific areas | Updated Grid on Controller's Office Year End Page to indicate down time for specific areas | Thursday | 2023-06-15 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson Amy Herron |  | Workday Business Process Downtime for FY2022 Year-End Close
Financial Accounting |  | GT | Send Key Year-End Campus Dates Email | Send Key Year-End Campus Dates Email (in the morning) (fin-all@office365.gatech.edu; Send email to Alana DeAngeleis) | Friday | 2023-06-16 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson |  |  | Created new controller's office email in order to send to fin-all group. New email is no-reply@business.gatech.edu
PCard |  | GT | FY23 - Final PCard Load - Transactions thru 6/15 Posted to Workday | PCard final load for fiscal year 2023 (transactions through 6/15/2023) | Friday | 2023-06-16 | Complete | Whittney Haynes Mike McCoy Timothy Hughes Chhaya Amin |  | Final load should be June 17th including all transactions made by June 16th. June 22nd is the final day for cardholders to verify the transactions that have been loaded to Workday | June 22nd is the final day for cardholders to verify the transactions that have been loaded to Workday
Expenses |  | GT | Final Travel Inc/AirPlus Bill for FY2023 Posted to the Ledger | Travel Inc/AirPlus bill from 6/14 posted to the ledger for FY23; travel after this date will be paid in FY24 | Friday | 2023-06-16 | Complete | Laura Jamison Jennifer Jacobs |  |  | Completed 6/15
SupplAccts |  | GT | Complete final direct airfare postings | Airline travel included in 6/14 Travel Inc/AirPlus bill will be posted to FY23 | Friday | 2023-06-16 | Complete | Laura Jamison Jennifer Jacobs Daniel Stewart |  |  | Completed 6/15
Security | SEC01a | GT/ATHL | CAMPUS - Supplier Invoice Requests CLOSED for FY23 REMOVE Security for Supplier Invoice Request Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Friday | 2023-06-16 | Complete | Marvin Petty Ruby Hollender Laura Jamison Tray Mathis Sabrena Nettles | Roles: Employee As-Self; Contingent Worker As-Self; Unit Receipt Creator; BPs: Supplier Invoice Request Event |  | Originally "OSP invoice data entry specialist" role was removed with campus on the 16th, after conversation w. Sheree Posey and Whitney Tate we concluded to not remove OSP security until 6/22. "OSP invoice data entry specialist" security was added back until 6/22.
Security | SEC01b | GT/ATHL | CAMPUS - Supplier Invoice Event CLOSED for FY23 REMOVE Security for Supplier Invoice Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Friday | 2023-06-16 | Complete | Marvin Petty Ruby Hollender Laura Jamison Tray Mathis Sabrena Nettles | Roles: Facilities Invoice Data Entry Specialist, Payroll Invoice Data Entry Specialist, OSP Invoice Data Entry Specialist, Supplier Contract Specialist BPs: Supplier Invoice Event |  | Per Whitney Tate: ROW 70 has no details – so Ruby/Marvin looked at THEIR list and found APDESK, OSPDESK etc. and that was NOT accurate. 70 should be REMOVED as it is notated in row 112 …we have no idea why 70 was there as campus cannot enter invoices.
Grants |  | GT | Over 90 day salary redistributions due to G&C | Over 90 day salary redistributions to externally funded sponsored projects due to Grants and Contracts | Friday | 2023-06-16 | Complete | Terryl Barnes Glenn Campopiano Josh Rosenberg |  |  | It is a deadline
Payroll |  | GT | MSS transactions Due - June Summer Semester Appointments - Regular Faculty | Manager Self-Service (MSS) transactions due for June summer semester appointment for regular faculty | Friday | 2023-06-16 | Complete | Jerri Phillips
Financial Accounting |  | GT | Send Invoice to GSFIC for Reimbursement | Send last invoice for the fiscal year to GSFIC for reimbursement of expenses charged to GSFIC projects. | Friday | 2023-06-16 | Complete | Julie Alvoid Amy Herron |  | The last invoice for the fiscal year was submitted on June 15, 2022 | Last reimbursement requests for FY23 sent to GSFIC on 6/15/23
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-06-16 | Complete | David Adcock | Friday - Saturday
Financial Accounting |  | GT | Deadline - Glass Shop EIBs/Journals for FY2023 | Deadline Glass Shop year-end transactions | Friday | 2023-06-16 | Complete | Julia Thomas | Carol to follow-up | The Glass Shop has not been in service this year as we are searching for a scientific glass blower. There has been no activity this year
Financial Accounting |  | GT | Deadline - Printing & Copying Services EIBs/Journals for FY2023 | Deadline Printing & Copying services year-end transactions | Friday | 2023-06-16 | Complete | Amanda Gooch Michael Teed
Security | SEC01c | GT/ATHL | CAMPUS - Expense Reports CLOSED for FY23 REMOVE Security for Expense Report Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) Initiating Action BP: Create Expense Report - Role: Employee as-self Initiating Action BP: Create Expense Report for Worker - Role: Expense Preparer Initiating Action BP: Create Expense Report for Non-Worker - Role: Expense Preparer Remove ability for ‘Employee as Self’ and 'Expense Preparers' to copy Expense Reports. Remove all access from Expense Preparer and remove only Modify access for Empl as Self to allow Employees to still view My Expense Reports delivered report. See 'View Security for Securable Item' for the 'Copy Expense Report' task. | Friday | 2023-06-16 | Complete | Marvin Petty Ruby Hollender Laura Jamison Tyler Dixon Yongmei Zhang Serena Simpson | Roles: Employee as Self; Contingent Worker as-self, Expense Preparer BPs: Expense Report Event |  | Expense Report Event - request by Michael Barnwell to do this task 1 hour earlier @ 4pm
Payroll |  | GT | Biweekly Staff and Student Pay Date - | Biweekly staff & student pay day | Friday | 2023-06-16 | Complete | Jerri Phillips
Procurement |  | GT | Last day to create small dollar catalog requisitions | Last day to create & approve a small dollar catalog REQ’s | Friday | 2023-06-16 | Complete | Erin Mitchell |  | This deadline has passed and the ability to create new requisitions has been removed
Security | SEC01d | GT/ATHL | CAMPUS - Requisitions CLOSED for FY23 - REMOVE Security for Requisition Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Friday | 2023-06-16 | Complete | Marvin Petty Ruby Hollender Whitney Tate Selinda Biggers | Role: Employee As-Self; RQ Reviewer
Security | SEC01d2 | GT/ATHL | CAMPUS - Requisitions CLOSED for FY23 - REMOVE Security for Requisition Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) BP: Requisition Initiating Action: Check-Out Remove: Employee-As-Self, RQ Reviewer | Friday | 2023-06-16 | Complete | Marvin Petty Ruby Hollender Whitney Tate Michael Barnwell Daniel Stewart
Security | SEC01e | GT/ATHL | CAMPUS - Requisitions CLOSED for FY2023 REMOVE Security for Requisition Event | Remove Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) Action Step: Review Requisition *Cost Center Manager *Management Chain *Manager *Requisition Requester *RQ Reviewer *Top Level Manager's Approver Action Step: Approve *Business Asset Accountant - Equipment *Business Asset Accountant - Non-Equipment *Business Asset Manager *Business Asset Surplus Manager *Cost Center Manager *Custodial Entity Manager *Designated Manager *Design Manager *Environmental Health & Safety *Gift Manager *Gift Portfolio Manager *Grant Manager *GTAA CFO *GTAA Compliance Group *GTAA - Equipment Manager *GTRI Business Asset Surplus Manager *GTRI Charge Code Manager *Manager *OM Manager *Primary Requestor Contact *Project Manager *Project Master *Top Level Manager's Approver | Friday | 2023-06-16 | Complete | Marvin Petty Ruby Hollender Whitney Tate Selinda Biggers |  | https://projects.edm.gatech.edu/browse/WKDAY-6811
Security | SEC01f | GT | Remove Shopping Access in Jaggaer | Whitney Tate turns off permissions to shopping tasks in Jaggaer on RQ Reviewer, GTRI Transaction View and Employee as Self. | Friday | 2023-06-16 | Complete | Whitney Tate | Per Michael Barnwell, changed date from 25th to the 18th.
Budgets |  | GT | Clear Transactions on "Undesignated" Driver Worktags | Clear transactions on undesignated driver worktags - Check daily | Friday | 2023-06-16 | Complete | Terryl Barnes Jason Cole Anagha Sahasrabudhe | 6/29/21 - Close to being cleared | https://projects.edm.gatech.edu/browse/WKDAY-6811
Grants |  | GT | Deadline for Written Cost Transfers < 90 days | Deadline for Written Cost Transfer Requests for Grants < 90 days | Tuesday | 2023-06-20 | Complete | Josh Rosenberg Glen Campopiano
Grants |  | GT | E-mail to PI's and Grant Administrators regarding Workday availability during year end close | Send notice to PI's and Grant Administrators regarding Workday down time for year end close | Tuesday | 2023-06-20 | Complete | Josh Rosenberg Amy Zhang |  | after controller office sending out the notification. | Controller's office sent out a notification to Fin-all this year on 6/15. G&C did not need to send.
Procurement |  | ATHL | Send list of GTAA Requisition mass closures to Athletics (Selinda) for verification | Send list of GTAA Requisition mass closures to Athletics (Selinda) for verification | Tuesday | 2023-06-20 | Complete | Whitney Tate Erin Mitchell Selinda Biggers
Procurement |  | ATHL | Athletics (Selinda) to cancel all Draft and In Process Requisitions | Cancel all Draft and In Process Requisitions | Tuesday | 2023-06-20 | Complete | Selinda Biggers Whitney Tate Erin Mitchell
Payroll |  | GT | Deadline - Late Timesheets for Biweekly Pay Periods Prior to 5/27 | Deadline - Late Timesheets for Biweekly Pay Periods Prior to 5/27 | Wednesday | 2023-06-21 | Complete | Jerri Phillips |  | 06.22.2022 - Per Jerri email confirmation.
Financial Accounting |  | GT | Deadline - Telecommunications EIBs/Journals for FY2023 | Deadline - Telecommunications EIBs/Journals for FY2023 | Wednesday | 2023-06-21 | Complete | Kat Vineyard Yongmei Zhang |  | 06.22.2022- Per Kat, Current person responsible telecom EIB Journal - Michael Cox
SupplAccts |  | GT | Invoice Match Exception Review | Invoices in match exception must be reviewed & action taken prior to this date | Thursday | 2023-06-22 | Complete | Laura Jamison Daniel Stewart |  | Abbie: Invoices have been reviewed. Campus still taking action 6/14 - Per Abbie, this is going to be ongoing until campus loses security. Revisit next year on Due date. 6/21- Per Abbie, security will be removed on June 22. | 6/13 - Laura, this is going to be ongoing until campus loses security.
Procurement |  | GT | Inform Zealy to Stop RPA Receipt Bot until July 5th | RPA Receipt Bot should be off from June 22nd - July 5th | Thursday | 2023-06-22 | Complete | Whitney Tate |  |  | [9:46 AM] Zealy, Daniel Tate, Whitney M and team, just a reminder we have paused the receipt bot after this mornings run. it will run again on the morning of 7/5.
Procurement |  | ATHL | Mass Close ALL GTAA Requisitions from FY21 | Mass Close ALL GTAA Requisitions from FY21 Company: CO5032 | Thursday | 2023-06-22 | Complete | Whitney Tate Erin Mitchell Selinda Biggers
Procurement |  | ATHL | Send list of PO mass closures to Athletics (Selinda) for Verification (4PM) | Send list of PO mass closures to Athletics (Selinda) for Verification (4PM) | Thursday | 2023-06-22 | Complete | Whitney Tate Erin Mitchell Selinda Biggers
Procurement |  | ATHL | Mass Close ALL GTAA Purchase Orders (4PM) | Mass Close ALL GTAA Purchase Orders Company: CO5032 PO Type: GTAA Alert Marvin Lewis that an approval is waiting for him | Thursday | 2023-06-22 | Complete | Whitney Tate Erin Mitchell Selinda Biggers
Procurement |  | ATHL | Send list of Athletics Purchase Order reconciliation to Controller's Office (4PM) | Send reconciliation to Controller’s Office Confirm all ATHL FY22 PO's are posted to the ledger - Cancel any PO's in process, draft, etc. "Provide June 30 Open Obligations By Company - CR report for ATHL by ChartField String - "Provide list of open PO Obligation balances as of June 30, 2023 to "gl.prodsupp@business.gatech.edu" and Daniel Stewart. List must reconcile to ledger | Thursday | 2023-06-22 | Complete | Whitney Tate Erin Mitchell Selinda Biggers |  | 06.22.2022 - Per Sellinda email about GTAA open obligation for FY22, need roll forward FY23. The amout of open PO amount match with GTAA GL balance.
PCard |  | GT | FY23 - Final PCard Verifications Due - Thru 6/15 | PCard Verifications (PCV) due for transactions through 6/15 | Thursday | 2023-06-22 | Complete | Whittney Haynes Erin Mitchell |  | Whittney is working on this. 6/28/2022- 52 transactions that did not get reconciled
Procurement | MASS_RQ1 | GT/ATHL | Mass Close ALL GT and ATHL BR23/FY23 Open Requisitions | Mass close ALL GT and ATHL open requisitions. Commitments must be zero at year end. | Thursday | 2023-06-22 | Complete | Whitney Tate Daniel Stewart Erin Mitchell Selinda Biggers |  | Complete for Athletics - Will complete tomorrow for GT. For next year we need to put this AFTER the change order buyer has been removed.
Security | SEC02 | GT/ATHL | CAMPUS - Receipts (Supplier Accounts) Closed for FY2023 - Campus REMOVE Security for Receipt Creator | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. Receipt Creator (@ 5PM) | Thursday | 2023-06-22 | Complete | Marvin Petty Laura Jamison Yongmei Zhang Tyler Dixon | Roles: Employee as self Contingent Worker as self Unit Receipt Creator Receipt Creator BP:Receipt
Security | SEC02a | GT | CAMPUS - Procurement Card Transaction Verifications Closed for FY23 - REMOVE SECURITY (Procurement Card Transaction Verification Event) | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Thursday | 2023-06-22 | Complete | Marvin Petty Whittney Haynes Yongmei Zhang Tyler Dixon | Roles: Employee As-Self BPs: Procurement Card Transaction Verification Event
Security | SEC02b | GT | CENTRAL- Purchase Order Event (Default Definition) CLOSED for FY23 REMOVE Security for Purchase Order Event (Default Definition) | Remove Central Office Security roles from Business Process Policy Initiation Steps so central office users cannot enter transactions. (@ 7AM) Roles: *Buyer - Change Order *Buyer - 500K *Buyer - GTRI *Buyer - GTRI Coordinator 10K *Buyer - Intermediate 150K *Buyer - Low 75K *Buyer - Purchasing Coordinator - 10K *Buyer - Senior Buyer - 250K *Buyer - Purchasing Coordinator - 25K | Thursday | 2023-06-22 | Complete | Marvin Petty Daniel Stewart Erin Mitchell Whitney Tate | Removed Procurement Manager Procurement Director Added: Purchasing Coordinator - 25K per Ruby Hollender | 6/22/2022 -All complete except Buyer - Change Order. Need one more day for that role. 6/28 - Whitney stated move forward with task.
Security | SEC02c | ATHL | CENTRAL - GTAA Purchase Order Event CLOSED for FY23 - REMOVE SECURITY REMOVE Security for GTAA Purchase Order Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 7AM) Role: Buyer | Thursday | 2023-06-22 | Complete | Marvin Petty Daniel Stewart Selinda Biggers Whitney Tate
Security | SEC02d | GT | CAMPUS - Purchase Order Event (Subaward) CLOSED for FY23 REMOVE Security for Purchase Order Event (Subaward) | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 7AM) Role: Subaward - Contracts Specialist | Thursday | 2023-06-22 | Complete | Marvin Petty Daniel Stewart Erin Mitchell Whitney Tate
Procurement |  | ATHL | Confirm all ATHL FY23 PO's are posted to the ledger | Confirm all ATHL FY23 PO's are posted to the ledger. Cancel any PO's in process, draft, etc. | Thursday | 2023-06-22 | Complete | Whitney Tate Selinda Biggers
Procurement |  | ATHL | Provide June 30 Open Obligations By Company - CR report for ATHL by ChartField String - | Provide list of open PO Obligation balances as of June 30, 2023 to "gl.prodsupp@business.gatech.edu" and Daniel Stewart. List must reconcile to ledger -run Open Obligation by Company Report | Thursday | 2023-06-22 | Complete | Whitney Tate Selinda Biggers Yongmei Zhang Serena Simpson
Security | SEC02e | GT/ATHL | CAMPUS - Spend Authorizations CLOSED for for FY23 REMOVE Security for Spend Authorization Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) Initiating Action BP: Create Spend Authorization - Role: Employee As Self Initiating Action BP: Create Spend Authorization for Worker - Role: Expense Preparer | Thursday | 2023-06-22 | Complete | Marvin Petty Yongmei Zhang Tyler Dixon Serena Simpson Laura Jamison | Roles: Employee as Self; Contingent Worker as-self, Expense Preparer, Expense Analyst BPs: Spend Authorization Event | Ruby will get OK from Business Service team to remove the campus security.
Procurement |  | ATHL | Verify all Athletics (GTAA) Requisitions have Zero Commitments | Verify all Athletics (GTAA) Requisitions have Zero Commitments Company: CO5032 | Thursday | 2023-06-22 | Complete | Whitney Tate Erin Mitchell Selinda Biggers
Expenses |  | GT | Deadline for FY2023 Spend Authorizations to be submitted and approved | Deadline for FY2023 Spend Authorizations to be submitted and approved | Thursday | 2023-06-22 | Complete | Laura Jamison Jennifer Jacobs |  | Per Abbie - This task will complete by 5pm 06.23.2022
Expenses |  | GT | Travel reimbursements for FY2023 Expense Reports will be processed through 4pm. | Travel reimbursements for Expense Reports will be processed through 4pm. Report must be approved and have all receipts and documentation. Expense reports that are not approved for payment in FY23 will be denied. | Thursday | 2023-06-22 | Complete | Laura Jamison Jennifer Jacobs | 6/25/21 Abbie: There were 4 expense reports out there this morning that we approved which will be picked up in the emergency settlement run today | Waiting for Abbie feedback
Financial Accounting |  | GT | Final Auxiliary Overhead Journals Posted to Ledger | Final Auxiliary Overhead Journals Posted to Ledger (This is the month-end Aux) | Thursday | 2023-06-22 | Complete | Sharon Serrano-Ahmed Brian Cochran | Sabrena completed 6/23/21 | This is the month end AUX
Financial Accounting |  | GT | Deadline Post Office Year-End Transactions | Deadline Post Office year-end transactions | Thursday | 2023-06-22 | Complete | Gwenda Bryant Yongmei Zhang | 6/28/21: PST_20210625_01 6/30/21: PST_20210629_01, PST_20210628_01 | Waiting for Gwenda confirmation
Security | SEC02f | GT/ATHL | Ad Hoc Payments CLOSED for FY23 REMOVE Security for Ad Hoc Payment Event | Remove campus security roles from Business Process Policy Initiation Steps users cannot enter transactions. (@ 5PM) ROLES: Accounts Payable Accountant Accounts Payable Data Entry Specialist Bursar Cash Manager Bursar Cash Specialist Cash Manager Facilities Invoice Data Entry Specialist OSP Invoice Data Entry Specialist PE Cashier PE Cash Manager Accounts Payable Analyst | Thursday | 2023-06-22 | Complete | Marvin Petty Laura Jamison Leanne Sheffield Selinda Biggers | Roles: Accounts Payable Accountant Accounts Payable Data Entry Specialist Bursar Cash Manager Bursar Cash Specialist Cash Manager Facilities Invoice Data Entry Specialist OSP Invoice Data Entry Specialist PE Cashier PE Cash Manager Accounts Payable Analyst
SupplAccts |  | GT/ATHL | Final FY2023 Payment Run | Final FY2023 Payment Run | Thursday | 2023-06-22 | Complete | Jeff Benenati Laura Jamison Selinda Biggers Daniel Stewart | Abbie to confirm with Jeff, possibly 12 6/25/21 Jeff: Will run at normal time. | Per Jeff - AP payment will run at noon 06.24.22 Bursars and GTAA plan to run the final payment 06.23.22.
Payroll |  | GT | Final FY2023 Off-Cycle Payroll Posted to the Ledger | Final FY2023 Off-Cycle Payroll Posted to the Ledger | Thursday | 2023-06-22 | Complete | Jerri Phillips Tyler Dixon
Procurement |  | GT | Mass close of BR19- BR22 PY Purchase Orders $500 or Less | Mass close of BR19 - BR22 PY PO's $500 or Less (Excluding PY OSP, construction, FF&E and R&M) | Friday | 2023-06-23 | Complete | Whitney Tate Erin Mitchell |  | 6/28/22 - Need to fix what is in error and revert back the budget checking BP before this is completed.
Procurement |  | GT | Mass close BR23 CY Purchase Orders $10 or Less | Mass close BR23 CY PO's of $10 or Less | Friday | 2023-06-23 | Complete | Whitney Tate Erin Mitchell |  | 6/28/22 - Need to fix what is in error and revert back the budget checking BP before this is completed.
Financial Accounting |  | GT | Balance Sheet Account Reconciliations Notification Email | Need reconciliations from all campus users with AR and/or Liability Accounts - Send notice to campus, but recon's cannot be completed until books are closed in Mid-July | Friday | 2023-06-23 | Complete | Tammy Putnal Leanne Sheffield | Completed 06.23.21 | 06.22.2022 - Per Tammy Balance Sheet Ledger Account Reconciliations are due on July 29, 2022 for FY22
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-06-23 | Complete | David Adcock | Friday - Saturday
Business Assets |  | GT | Lease Equipment - Reconcile Common Book to Capital Book for lease activity | Lease Equipment - Reconcile Common book to Capital book for lease activity - Ongoing throughout year - send email to Property Control to set up leased pieces of equipment. | Friday | 2023-06-23 | Ongoing | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur
Expenses | EXP1 | GT/ATHL | Cancellation of Expense Reports for FY23 | Cancellation of Draft and In Progress Expense Reports for GT and GTAA. For GT, verify file has been created for reloading Spend Authorizations before canceling Expense Reports. | Friday | 2023-06-23 | Complete | Laura Jamison Jennifer Jacobs Michael Barnwell Selinda Biggers |  |  | Complete for CO503 and CO5032.
Procurement | MASS_RQ2 | GT/ATHL | Confirm all GT and ATHL FY2023 Requisition Commitments are Zero in Procurement System | Run "Requisition Line Commitment - CR" report for CO503. Confirm "Commitment Amount Remaining" balance is zero for all requisitions. ---notify gl.prodsupp@business.gatech.edu when complete | Friday | 2023-06-23 | Complete | Whitney Tate Daniel Stewart Erin Mitchell Selinda Biggers | 5 requisitons have a balance; Whitney and Daniel working on resolving (RQ-1087487,RQ-1096180,RQ-1146844,RQ-1150297,RQ-1156572) 6/28/21 - Reopen and close them but trial balance will be effected. 6/29- All were reopened and closed with the exception of RQ-1087487 (due to it being FY20) |  | I have added GTAA committment Ledger to the files.
SupplAccts |  | GT | Create Commitment Journals to Zero FY23 Program Advances | Create Commitment Journals to Zero Program Advances that are still open in FY23 at year end ---Confirm amount with Yongmei Zhang and Nate Watkins prior to entering journal | Friday | 2023-06-23 | Complete | Liliana Blettler Yousaf Farhat Laura Jamison Nate Watkins Daniel Stewart | IM Carol Gibson when Yousaf has approved for Controller's Office approval; 6/25/21 - Carol approved and now in Yousaf's queue; Yousaf approved and commitment is now zero | Journals created and awaiting approval from Controllers office. Yousaf sent message in Closeout Teams channel.
Financial Accounting | MASS_RQ3 | GT/ATHL | Verify Requisiton Commitments are Zero on the Ledger for FY2023 | Run "Trial Balance" for the Commitment Ledger for each company. View to ensure commitments are zero. If not, run "Find Journal Lines - CR" report for the Commitment Ledger to get detail. All Commitments from Requisitions should be zero at year end. They cannot carry forward. ---Look at all source codes | Friday | 2023-06-23 | Complete | Yongmei Zhang Serena Simpson Antinina Wilkerson
Expenses | MASS_SA1 | GT/ATHL | Mass close FY2023 spend authorizations | Run report of Spend Authorizations to load in new Fiscal Year and save file Cancel all Draft and In Progress Spend Authorizations Mass close all Approved Spend Authorizations | Friday | 2023-06-23 | Complete | Michael Barnwell Laura Jamison Jennifer Jacobs Selinda Biggers |  |  | Complete for CO503 and CO5032.
Expenses | MASS_SA2 | GT/ATHL | Confirm all FY2023 Spend Authorization Commitments are Zero in Expenses System | Run "Find Spend Authorizations - CR" report for CO503 and CO5032. Confirm "Commitment Amount Remaining" balance is zero for all spend authorizations. ---send reports to "gl.prodsupp@business.gatech.edu" | Friday | 2023-06-23 | Complete | Michael Barnwell Laura Jamison Jennifer Jacobs Selinda Biggers Nate Watkins Liliana Blettler | 6/25/21 - Courtney posted journals to correct the program advances: JE-0000013288,JE-0000013289,JE-0000013290 | Remaining Commitment amount for GT is only Program Advances. Journals were created for these to move the commitment. For GTAA, no Approved Spend Auths are remaining for FY22. | CO503: Find Spend Authorizations - CR Report shows only Program Advances remaining. The Commitment Amount Remaining is $479,215.55. This matches the Ending Balance on the Trial Balance Report for Acct 381104. Journal Entries are being created for these Program Advances. CO5032: Trial Balance shows a zero balance for account 381104.
Financial Operations |  | GT/ATHL | Meet with FinOps to review Scheduled Processes | PayCycle, Bank Files, etc. | Friday | 2023-06-23 | Complete | Verlencia Haynes Jeff Benenati Antinina Wilkerson Yongmei Zhang Tyler Dixon Serena Simpson Amy Herron Chhaya Amin Michael McCoy Timothy Hughes | Meeting 6/25/21; 6/25/21 - Jeff: Bursar wants to run a process tonight
Grants |  | GT | Review Restricted Fund Transactions | Ensure no Fund Balance at YrEnd Close; Move Fund Balance to receivable - Cleanup for fiscal year end | Friday | 2023-06-23 | Complete | Josh Rosenberg Glen Campopiano |  | 6.22.22: no activity in fund balance (Acct. 341100) this fiscal year so complete for FY22; working on reviewing balances carried over from prior year activity.
GTRI |  | GT | Deadline GTRI Machine Shop Charges | Deadline GTRI Machine Shop Charges | Friday | 2023-06-23 | Complete | Alice Fellabaum April Howze Julie McCoy | 6.25.21 April: Expect to post Machine shop EIB Monday 28th GTI_20210628_01
Payroll |  | GT | Pay Date - Final Off-Cycle Pay Checks | Pay Date - Final Off-Cycle Pay Checks | Friday | 2023-06-23 | Complete | Jerri Phillips
Procurement |  | GT | Confirm all GT FY23 PO's are posted to the ledger | Confirm all GT FY23 PO's are posted to the ledger. Cancel any PO's in process, draft, etc. | Friday | 2023-06-23 | Complete | Whitney Tate Erin Mitchell |  | 6/28/22 - Waiting on Workday fix can not proceed.
Procurement |  | GT | Provide June 30 Open Obligations By Company - CR report for GT by ChartField String - | Provide list of open PO Obligation balances as of June 30, 2023 to "gl.prodsupp@business.gatech.edu". List must reconcile to ledger -run Open Obligation by Company Report | Friday | 2023-06-23 | Complete | Whitney Tate Selinda Biggers Yongmei Zhang Serena Simpson |  | 6/28/22 - Waiting on Workday fix can not proceed.
Financial Accounting |  | GT | Fix GT Operational Journals in Error | Run proccess and fix all journals after Procurement has finished with all close processes. | Friday | 2023-06-23 | Ongoing | Tyler Dixon Yongmei Zhang Serena Simpson |  | 6/28/22 - Waiting on Workday fix can not proceed.
Financial Accounting |  | ATHL | Fix ATHL Operational Journals in Error | Run process and fix all journals after procurement has finished with all closed processes. | Friday | 2023-06-23 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson
Procurement |  | GT | Close Non-PO Supplier Contracts | Close supplier contracts that create Obligations but do not create Purchase Orders ---notify gl.prodsupp@business.gatech.edu when complete | Friday | 2023-06-23 | Complete | Whitney Tate Nate Watkins | SCN-00003760 | 6/28/22 - - Whitney ,this has been complete
Financial Accounting | MASS_SA3 | GT/ATHL | Verify Spend Authorization Commitments for FY23 are Zero on the Ledger | Run "Trial Balance" for the Commitment Ledger for each company. View to ensure commitments are zero. If not, run "Find Journal Lines - CR" report for the Commitment Ledger to get detail. All Commitments from Requisitions should be zero at year end. They cannot carry forward. ---Look at all source codes | Friday | 2023-06-23 | Complete | Yongmei Zhang Serena Simpson Antinina Wilkerson
Security | SEC03 | GT | CAMPUS - Purchase Order Event (Facilities) CLOSED for Facilities for FY2023 REMOVE Security for Purchase Order Event (Facilities) | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) Role: Facilities Contract Buyer | Friday | 2023-06-23 | Complete | Marvin Petty Daniel Stewart Erin Mitchell Whitney Tate |  | This should be THE SAME DAY as Central Procurement. Please update for next FY.
Security | SEC03a | GT/ATHL | CENTRAL - Supplier Invoices CLOSED for FY23 REMOVE Security for Supplier Invoice Event | Remove central office security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Friday | 2023-06-23 | Complete | Marvin Petty Tray Mathis Sabrena Nettles Laura Jamison | Roles: Account Payable Invoice Data Entry Specialist BP:Supplier Invoice Event | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22 - Complete this morning
Security | SEC03b | GT | CAMPUS - Supplier Contract Event CLOSED for FY2023 REMOVE Security for Supplier Contract Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Friday | 2023-06-23 | Complete | Marvin Petty Erin Mitchell Daniel Stewart | Roles: Real Estate Contract Specialist BPs: Supplier Contract Event
Security | SEC03c | GT | CAMPUS - Supplier Contract Amendments CLOSED for FY23 REMOVE Security fro Supplier Contract Amendment Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Friday | 2023-06-23 | Complete | Marvin Petty Erin Mitchell Daniel Stewart | Roles: Real Estate Contract Specialist BPs: Supplier Contract Amendment Event
Security | SEC03d | GT/ATHL | CAMPUS - Asset Issue Event and Asset Transfers CLOSED for FY23 REMOVE Security for Asset Issue Event and Asset Transfer Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Friday | 2023-06-23 | Complete | Marvin Petty Kelly MacArthur Fredrick Trotter Tanisha Tigner | Roles: Business Asset Tracking Specialist BPs: Asset Issue Event; Asset Transfer Event
Security | SEC03e | GT | CAMPUS - Budget Amendments for Projects CLOSED for FY23 REMOVE Security for Budget Amendment Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Friday | 2023-06-23 | Complete | Marvin Petty Maurena Maynor Antinina Wilkerson Nate Watkins Doug Feller Josh Rosenberg | Roles: Cost Center Manager, Gift Manager, Grants Manager, Grants Budget Amendment Creator, Project Master BPs: Budget Amendment Event
Financial Accounting |  | GT | Remove Spend Authorization critical Custom Validation called 'Justification Required for Late Travel' until after Spend Authorization Load is complete | Remove Spend Authorization critical Custom Validation called 'Justification Required for Late Travel' until after Spend Authorization Load is complete. This can occur anytime after campus access to Expenses is removed. | Friday | 2023-06-23 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson
All |  | GT/ATHL | Add Messaging for no approvals | Send Messaging about not approving Supplier Invoices in your Workday inbox until GT is open for FY2024 on Wednesday, July 5. | Friday | 2023-06-23 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson |  | Sent out 6/27/2022 @6:15PM
SupplAccts |  | GT | Verify all Payments for FY2023 posted | Verify all Payments are posted correctly | Friday | 2023-06-23 | Complete | Laura Jamison Whitney Tate Daniel Stewart |  | 6/28/22 - Waiting on Workday fix can not proceed.
SupplAccts |  | GT | Reconcile Payables Accounts for FY2023 | Reconcile Clearing Accounts and Receivable Accts | Friday | 2023-06-23 | Complete | Yousaf Farhat Laura Jamison Daniel Stewart | 6/29/21- Still working on it 6/30/21 - Still in Progress | 6/28/22 - Waiting on Workday fix can not proceed.
SupplAccts |  | GT | Verify AP Liability Ledger Account (211400) Balance is Correct on the Ledger | Verify AP Liability Ledger Account (211000) Balance is Correct on the Ledger - Reconcile open liabilities | Friday | 2023-06-23 | Complete | Yousaf Farhat Laura Jamison Daniel Stewara |  | AP Liability Ledger Account is 211000. 211400 was in PS. 6/28/22 - Waiting on Workday fix can not proceed.
Financial Accounting | VERIFY1 | GT | Reconcile GT Requisition Commitments on Ledger to Requisition Commitments in Procurement System | Run "Find Journal Lines - CR" report for the Commitment Ledger. Run "Trial Balance " report. Run "Find Spend Authorizations - CR" report. All Commitments from Requisitions should be zero at year end. They cannot carry forward. ---Look at all source codes | Saturday | 2023-06-24 | Complete | Yongmei Zhang Serena Simpson | Find Spend Authorizations -> Spend Authorization status: Draft, In Progress, Approved AUTH-1025209 (2500.00),AUTH-1025346(1,500.00), AUTH-1025922(110000) JE-0000013290 | 6/30/22- Will complete today
Financial Accounting | VERIFY2 | ATHL | Reconcile ATHL Requisition Commitments on Ledger to Requisition Commitments in Procurement System | Run "Find Journal Lines - CR" report for the Commitment Ledger. Run "Trial Balance" report. Run "Find Spend Authorizations - CR" report. All Commitments from Requisitions should be zero at year end. They cannot carry forward. ---Look at all source codes | Saturday | 2023-06-24 | Complete | Yongmei Zhang Serena Simpson | ATHL: AUTH-1015619 -57.57
Financial Accounting | VERIFY3 | ATHL | Reconcile ATHL PO Obligations on Ledger to Open Obligation by Company - CR report - Balance should be ZERO | Run "Find Journal Lines - CR" report for the Obligation Ledger. Run "Trial Balance - Composite" report. Run "Open Obligation by Company - CR" report. ATHL Obligations should be zero at year end | Saturday | 2023-06-24 | Complete | Yongmei Zhang Serena Simpson | Trial Balance zero; 9 PO's carry forward | 6/30/22- Will complete today
Financial Accounting | VERIFY4 | GT | Confirm Payroll/Personal Services Obligations for FY2023 are Zero on the Ledger | Run "Find Journals Lines - CR" report to see if any Commitment Accounting transactions (Source Code ENC) have Obligation balances. Create EIB journal to remove encumbrances if any remain. (@ 5PM) There may be PO Obligations in the following Ledger Accounts - 539200 (Dual Employment - Staff), 555100 (Unemployment Insurance), 556100 (Workers Compensation), 569100 (Misc Personal Services). Those are okay. | Saturday | 2023-06-24 | Complete | Yongmei Zhang Serena Simpson |  | 6/30/22- Will complete today
Financial Accounting | VERIFY5 | GT | Reconcile GT Spend Authorization Commitments on Ledger to Spend Authorization Commitments in Expenses System | Run "Find Journal Lines - CR" report for the Commitment Ledger. Run "Trial Balance - Composite" report. Run "Requisition Line Commitment - CR" report. All Commitments from Spend Authorizations should be zero at year end. They cannot carry forward. ---Look at all source codes | Saturday | 2023-06-24 | Complete | Yongmei Zhang Serena Simpson |  | 6/30/22- Will complete today
Financial Accounting |  | GT | First Review of POOELS | First Review Purchase Order Obligations and Expense Report to see if there are liquidation issues | Saturday | 2023-06-24 | Complete | Amry Stanley Christopher Drummond |  | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22- Will complete today
Financial Accounting | VERIFY6 | GT/ATHL | Verify FY23 PO Obligation Ending Balance matches to FY24 PO Obligation Beginning Balance | Verify FY23 PO Obligation Ending Balance matches FY24 PO Obligation Beginning Balance (Trial Balance Report) - Also check run sheet; certain periods and books must be open | Saturday | 2023-06-24 | Complete | Yongmei Zhang Serena Simpson |  | CHECK RUN SHEET. CERTAIN BOOKS AND PERIODS MUST BE OPEN BEFORE WHITNEY CAN RUN; 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22- Will complete today
Procurement |  | GT/ATHL | Procurement Purchase Order Roll Forward of FY19, FY20, FY21,FY22 and FY23 (budget ref) Purchase Order Obligations ***PO's must be reconciled to the ledger first!! Please work with Financial Accounting team on parameters and options before rolling forward balances. | Procurement PO Roll Forward FY19, FY20, FY21,FY22 and FY23(budget ref) Purchase Order Obligations - GT and ATHL into the new fiscal year Verify Ledger Account for Reserve for Obligations for FY2024 is 381102 in Ledger Posting Rules PO's cannot be rolled into a different Budget Reference. Accounting information on PO's cannot be changed. | Saturday | 2023-06-24 | Complete | Daniel Stewart Whitney Tate Erin Mitchell |  | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22- Will complete today
Financial Accounting | VERIFY7 | ATHL | Reconcile ATHL Spend Authorization Commitments on Ledger to Spend Authorization Commitments in Expenses System | Run "Find Journal Lines - CR" report for the Commitment Ledger. Run "Trial Balance" report. Run "Requisition Line Commitment - CR" report. All Commitments from Spend Authorizations should be zero at year end. They cannot carry forward. ---Look at all source codes | Saturday | 2023-06-24 | Complete | Yongmei Zhang Serena Simpson
Financial Accounting | VERIFY8 | GT | Reconcile GT PO Obligations on Ledger to Open Obligation by Company - CR report | Run "Find Journal Lines - CR" report for the Obligation Ledger. Run "Trial Balance - Composite" report. Run "Open Obligation by Company - CR" report. | Saturday | 2023-06-24 | Complete | Yongmei Zhang Serena Simpson | Obligations on TB match to Open Obligation by Company report. When Receipts in "inbox", action can still be taken to "Approve"; 6/30/21 - Casey: Sending out communication to not approve receipts | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22- Will complete today
Financial Accounting |  | GT/ATHL | Update Ledger Period Status to Close in Progress Procurement (Everything else open) for FY2023 for GT/ATHL | Update Ledger Period Status to Close in Progress Procurement (Everything else open) for FY2023 for GT/ATHL Must happen after all PO's and Requisitions are complete by Procurement Team | Saturday | 2023-06-24 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson | Closed Activity: Procurement There are 4 requisitions pending: RQ-1164165,1165003,1167214,1168821 (Action: Whitney to cancel) | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22 - Can complete now
Commitment Accounting |  | GT | Load GT Budget Prep staging tables for new Fiscal Year | Load GT Budget Prep staging tables for new Fiscal Year (FY2024). Merge GT Original Budget data with CA & HR data. Check for Inactive Projects, and verify load. | Monday | 2023-06-26 | Complete | Richard Tanner Terryl Barnes Jason Cole Anagha Sahasrabudhe |  |  | Per Richard, this item should be done by Friday 6/30.
Payroll |  | GT | Deadline - Biweekly Timesheets for Period Ending 6/24 | Deadline for timesheets - Biweekly pay period ending 6/24 | Monday | 2023-06-26 | Complete | Jerri Phillips | 6/28/21 - Pending
Financial Accounting |  | GT | Final BuzzCard Journal Entries for FY2023 | Final posting from BuzzCard Center 4pm | Wednesday | 2023-06-28 | Complete | Bob Junko | Kimberly Segal: Our bulk entries that would hit other departments are complete as of 6/25. We are still posting internal entries by today’s deadline and they default to the BuzzCard Journal option. We can make it an online journal as a posting instead if you like. We have a few more of these per our account reconciliations. They will be posted by 4p today. | all BuzzCard JE's are done | Per Bob Junko on 6/23: This task should be done early next week. 6/27 Update: processing additonal JE's will be done by 6/28 deadline. This task will be moved to the 6/28 accounting journal deadline.
Commitment Accounting |  | GT | Liquidate Salary Obligations (Encumbrances) | Liquidate any outstanding salary obligations (encumbrances) in Workday Financials | Wednesday | 2023-06-28 | Complete | Terryl Barnes Jason Cole Anagha Sahasrabudhe Chhaya Amin | 6/28/21 - File posted
Grants |  | GT | F&A Rates FY2024 | Load and verify new F&A Rates have been added to Workday | Wednesday | 2023-06-28 | Complete | Tony Wang Neli Tranakiev Amy Zhang Jonathon Jeffries | 6.21.21: Jonathon (Don was working on the FY22/FY23 fringe agreement in WD this morning.) Completed 6.22.21 | 6/14/22 - Per Amy: The current F&A rate is for both FY22 and FY23. so we don't need to update anything this year. | Provisional FA rate for FY24 has been update to WD on 6/23/2023. (this is contingent on approval from the Feds) Grants and Contracts has reached out to our Federal POC they have indicated we will have new rates approved by the end of June.
Grants |  | GT | Provide New FY2024 Overhead Rates | Provide new overhead rates and fringe rates for FY2024. Send information through commitment accounting mail groups and Workday for distribution to campus. | Wednesday | 2023-06-28 | Complete | Josh Rosenberg Jonathon Jeffries | Date is really contingent on ONR. |  | Grants and Contracts has reached out to our Federal POC they have indicated we will have new rates approved by the end of June.
Financial Accounting |  | GT | Monitor financial activity for blank and old Budget References (BR19,BR20,BR21,BR22) only | Monitor financial activity for blank and old Budget References (BR19,BR20,BR21,BR22) | Wednesday | 2023-06-28 | Ongoing | Yongmei Zhang Tyler Dixon Serena Simpson
Commitment Accounting | BWACC2 | GT | Generate Transactions and Provide Biweekly Payroll Accrual EIB File to Workday/Financial Accounting for FY2023 | Generate Transactions and Provide Biweekly Payroll Accrual EIB File to Workday/Financial Accounting for FY2023 | Wednesday | 2023-06-28 | Complete | Terryl Barnes Jason Cole Anagha Sahasrabudhe
Financial Accounting |  | GT | Deadline for all EIB Upload Journals from Service Centers and Central Business Office for FY2023 (excluding GTPE) | Deadline for all EIB Upload Journals from Service Centers and Central Business Office for FY2023 (excluding GTPE) | Wednesday | 2023-06-28 | Complete | Tyler Dixon Yongmei Zhang |  | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22- Will complete today
Financial Accounting |  | GT/ATHL | Deadline - Accounting Journals and Adjustments (Create Journals) - Campus | Deadline - Accounting Journals and Adjustments (Create Journals) - Campus | Wednesday | 2023-06-28 | Complete | Tyler Dixon Yongmei Zhang |  | 6/28/22 - Waiting on Workday fix can not proceed.
Financial Accounting |  | GT/ATHL | Deadline for Operational Accounting Adjustments for FY2023 - Expense Reports, Supplier Invoices, etc. | Deadline for Operational Accounting Adjustments for FY2023 - Expense Reports, Supplier Invoices | Wednesday | 2023-06-28 | Complete | Tyler Dixon Yongmei Zhang |  | 6/28/22 - Waiting on Workday fix can not proceed.
Security | SEC04 | GT/ATHL | CAMPUS - Accounting Journals CLOSED for FY23 REMOVE Security for Accounting Journal Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Wednesday | 2023-06-28 | Complete | Marvin Petty Ruby Hollender Tyler Dixon Yongmei Zhang | Roles: Accountant; Accountant - Campus Service Center; Accountant - Central Business Office BPs: Accounting Journal Event | 6/28/22 - Waiting on Workday fix can not proceed. 06/30/22 - security removed per Carol Gibson
Security | SEC04a | GT/ATHL | CAMPUS - Accounting Journal Adjustments CLOSED for FY23 REMOVE Security for Accounting Adjustment Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Wednesday | 2023-06-28 | Complete | Marvin Petty Ruby Hollender Tyler Dixon Yongmei Zhang | Roles: Accountant BPs: Accounting Adjustment Event | 6/28/22 - Waiting on Workday fix can not proceed. 06/30/22 - security removed per Carol Gibson
Various |  | GT | Clear Bank Reconciliation Items Through May 2023 | Make corrections as necessary to remove outstanding items from the Operating Bank Recon | Wednesday | 2023-06-28 | Ongoing | Leanne Sheffield Maurena Maynor Curlyne Andrews Yousaf Farhat
Various |  | GT | Clear Allocation for FRF | Make corrections as necessary to clear allocation for FRF | Wednesday | 2023-06-28 | N/A | Lee Wates Maurena Maynor Amy Herron |  | 7/6/22 - TBD | 3/17/2023 - Maurena stated the item may not be necessary because of Lee’s correction to the allocation process.
Payroll |  | GT | Final FY2023 Monthly Payroll Posted to the Ledger | Final FY2023 Monthly Payroll Posted to the Ledger | Wednesday | 2023-06-28 | Complete | Jerri Phillips Yongmei Zhang | 6.22.21 - Terryl: Monthly Payroll experiencing USG issues. 6.23.21 - Currently processing | 6/30/2022 - Final EDR, FRF will post on Saturday (July 2, 2022)
Bursar/Treasury |  | GT | Deadline for Cash Receipts - 4PM | Deadline for FY2023 Cash Receipts 4pm | Wednesday | 2023-06-28 | Complete | Curlyne Andrews | 6/29/21 - Will Be completed Today
Payroll |  | GT | Biweekly Pay Period End Date - Pd Ending 6/24 | Biweekly Pay Period End Date | Wednesday | 2023-06-28 | Complete | Jerri Phillips
Payroll |  | GT | Biweekly Payroll Posted to Ledger - Period Ending 6/24 | Biweekly Payroll Posted to Ledger - Period Ending 6/24 | Wednesday | 2023-06-28 | Complete | Jerri Phillips | (Accrual was posted already; through 6/30) | 6/30/22 - Confirmed with Terrly this will post in July; waiting next week to post accural and will hold and post this journal when FY23 open.
Security | SEC04b | GT/ATHL | CAMPUS - Accounting Journal Unpost/Reverse CLOSED for FY23 REMOVE Security for Accounting Journal Unpost-Reverse Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Wednesday | 2023-06-28 | Complete | Marvin Petty Ruby Hollender Tyler Dixon Yongmei Zhang | Roles: Accountant BPs: Accounting Journal Unpost-Reverse Event | 6/28/22 - Waiting on Workday fix can not proceed. 06/30/22 - security removed per Carol Gibson
Security | SEC04c | GT/ATHL | CAMPUS - Accounting Copy Journal Action CLOSED for FY23 REMOVE Security for Copy Journal Action | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Wednesday | 2023-06-28 | Complete | Marvin Petty Ruby Hollender Tyler Dixon Yongmei Zhang | Roles: Accountant Actions: Copy Journal Action | 6/28/22 - Waiting on Workday fix can not proceed. 06/30/22 - security removed per Carol Gibson
Financial Accounting |  | GT/ATHL | Update Ledger Period Status to "Close In Progress" for Operational Accounting for FY2023 - JUNE for GT | All Operational Journals in Error must be fixed!!! Update Ledger Period Status - Operational Accounting (Close in Progress) Must happen after final Journals from campus deadline Central Office can still process Operational Accounting Journals for Invoices and expense reports for June FY23. They will go into an error status and then will need to be fixed via the "Fix Operational Journals in Error" process in FY23. Must happen after security is removed from campus users for journals for FY23 (accounting journals, accounting journal adjustments, copy journals, unpost/reverse journals). **This can not be done before 5PM | Wednesday | 2023-06-28 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson | ATHL - Asset Journal GT - Asset Journals 6/29/21 - Selinda will cancel her JE and Frederick will circle back with Harold and team. 6/30/21 - ATHL and GT Asset journals gone |  | (combine this task with "exepnses" update ledger period task, below)
Financial Accounting |  | GT/ATHL | Update Ledger Period Status to Close in Progress: Expenses (Travel) for GT/ATHL | Update Ledger Period Status FY23-JUN Close in Progress: Expenses Must happen after all Spend Authorizations and Expense Reports are complete by Expenses Team **This can not be done before 5PM | Wednesday | 2023-06-28 | Complete | Tyler Dixon Yongmei Zhang | Closed Activity: Expenses 6/30/21 - Selinda request to stay open for all of her months till she reconciles. She will notify Controller's office when she is done | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22 - Can complete | Per a meeting with Carol Gibson on 6/27, this can be moved to 6/28 to coincide with "operational accounting" ledger status. Confirmed with Laura Jamison.
IEN |  | GT | Deadline for ELN Charges | Final Posting of FY2023 Electronic and Nanotechnology Charges (ELN) | Thursday | 2023-06-29 | Complete | Braxton Bragg Kristin Turgeon Roy Wood Chhaya Amin | 6.24.21 - ELN_20210624_03 6.28.21 - Last file to process (cut off should've been 25th) ELN_20210627_01,02,03
Financial Accounting | BWACC1 | GT | Verify Biweekly Payroll Accrual EIB File (EDR) to the Ledger - FY2023 | Verify BWACC2 - Post Biweekly Payroll Accrual EIB File (EDR) to the Ledger | Thursday | 2023-06-29 | Complete | Tyler Dixon Yongmei Zhang | Update: Terryl's step completed 6/22/21
Financial Accounting |  | GT | Final Review Purchase Order Obligations and Expense Report | Final Review Purchase Order Obligations and Expense Report; run final report after PO Reconciliation is complete. | Thursday | 2023-06-29 | Complete | Christopher Drummond Amry Stanley |  | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22 - Can complete now
Financial Accounting | PYPO1 | GT | PYPO/SURPLUS - EIB Load - Move Funds to Surplus Balance Sheet Ledger Account for Non-Sponsored Funds | EIB Load - Move Funds to Surplus Balance Sheet Ledger Account for Non-Sponsored Funds. Enter PO number in External Reference ID Field | Thursday | 2023-06-29 | Complete | Christopher Drummond Amry Stanley Yongmei Zhang Tyler Dixon |  | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22 - This can be completed today
Financial Accounting | PYPO2 | GT | PYPO/SURPLUS - EIB Load - Reduce CarryForward Budgets by Surplus Amount for Non-Sponsored Funds | EIB Load - Reduce CarryForward Budgets by Surplus Amount for Non-Sponsored Funds. Enter PO number in Memo Field. | Thursday | 2023-06-29 | Complete | Christopher Drummond Amry Stanley Antinina Wilkerson Nate Watkins Yongmei Zhang |  | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22 - This can be completed today
GTRI |  | GT | Deadline GTRI Services to RI Units | Deadline GTRI Services to RI Units | Thursday | 2023-06-29 | Complete | Alice Fellabaum April Howze Julie McCoy
Financial Accounting |  | GT | Confirm with ServiceNow or Budget Office - Catalog Item need pause | ServiceNow Portal for GTPE CRS need to stop before the new Budget reference update. | Friday | 2023-06-30 | Complete | Yongmei Zhang Tyler Dixon Serena Simpson |  |  | [Thursday 9:41 AM] Reyes, Chris Per Chris message- GT project go live date is tentatively set on July 14, but what I know from the project duration, CTEK should start their deployment by July 5 to prepare for technical release. Note: Next year, we need to stop integration or take servicenow form down while loading new budget years. *Dennis Handy has made a note that he will not post any entries on 6/30
Financial Accounting & Grants |  | GT | Confirm with G&C that they have rescheduled the bot to run on July 12th | Check with Grants and Contracts team to ensure they have rescheduled the bot to run on July 12th so it does not impact YE. | Friday | 2023-06-30 | Complete | Amy Zhang Yongmei Zhang Serena Simpson Tyler Dixon
Commitment Accounting |  | GT | Deadline - Express Direct Retro (EDR) salary distribution changes for FY2023 - Campus | Deadline to process Express Direct Retro (EDR) salary distribution changes - Campus | Friday | 2023-06-30 | Complete | Terryl Barnes Jason Cole Anagha Sahasrabudhe Jana Wagner | 6/29/21 - Jason sent out a reminder this morning. EDR's will be stopped tomorrow at 4:45PM; 7/1/21:EDR nightly process failed. Referesh will happen again; posted successfully | 6/30/22 - This will post on Friday July 1, 2022
Grants |  | GT | Deadline - New Award Lines/Grants/Attributes | Deadline - New Award Lines/Grants/Attributes | Friday | 2023-06-30 | Complete | Josh Rosenberg | Glenn to check with Gabbie
Payroll |  | GT | Monthly Staff Pay Date - Period Ending 6/30/23 | Monthly Staff Pay Date - Period Ending 6/30/23 | Friday | 2023-06-30 | Complete | Jerri Phillips
Business Assets |  | GT | Finalize Finance Lease Recon | Finalize finance lease recon and all associated adjustments to all books (i.e., review Ledger detail to see if anything posted after completing recon on June 14). | Friday | 2023-06-30 | Ongoing | Kelly MacArthur Holly Seel Amy Herron | (In conjunction with task: Capital Lease Recon - Reconcile payments for Capital Leases to lease payment schedules) | 6/30/22 - Kelly M. will let us know when this is completed
Financial Accounting |  | GT | Verify FD00000 has no posted transaction to the fund. | Verify FD00000 has no posted transaction to the fund. | Friday | 2023-06-30 | Complete | Maynor Maurena
Financial Accounting |  | GT | Send out email to Central office when canceling journals | Sent out an email to Central office groups to let them know that their journals will be canceled and they need to post their journals before we open for new Fiscal Year | Friday | 2023-06-30 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson |  | 07/05/2022 - This will be new for FY23
Financial Accounting |  | GT | Cancel Journals from Campus Units | Only Controller's Office, Grants, GTRI, Budgets,AUX, and GTPE should be able to create journals. All others need to be canceled by 4pm. | Friday | 2023-06-30 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-06-30 | Complete | David Adcock | Friday - Saturday
Various |  | GT | Write-off uncollectible receivable accounts for FY2023 ($3,000 or less) | Write-off uncollectible receivable accounts ($3,000 or less) | Friday | 2023-06-30 | Complete | Gloria Kobus Jim Pierce Josh Rosenberg Julie McCoy | 7/6/21 - No write-offs for GTRI | None for RI. | None for RI.
Financial Accounting |  | GT | Perform Year End Inventory Count | Count inventory at June 30, 2023 and provide count to Controller's Office | Friday | 2023-06-30 | Complete | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur David Goldfarb John Scuderi Bob Junko Donald Johnson |  | 7/5/22 @4:09PM - This will be completed today.
Payroll |  | GT | Biweekly Staff and Student Pay Day | Biweekly Staff and Student Pay Day | Friday | 2023-06-30 | Complete | Jerri Phillips
OIT |  | GT | ServiceNow GTPE Course Section Request takedown | ServiceNow GTPE Course Section Request takedown (will be added back July 3, 2023) | Friday | 2023-06-30 | Complete | Alex Agle Alpha Team (Service Now Support Group) Erik Powell vdarapu3 Tyler Dixon Yongmei Zhang |  |  | This task is for FY24. This year Yongmei will send an email to Lamar Handy and ask him to stop adding GTPE Projects on June 30th. He can start again when we open for July 3, 2023. (Process next year is to put in a ServiceNow ticket)
Financial Accounting |  | GT | Send Template for journals for BR23 | Send template to the closing groups (gtri, grants, gtpe, etc) and note they need to use this starting in July to close June of the prior year. (with BR23) | Friday | 2023-06-30 | Complete | Tyler Dixon Yongmei Zhang | Added this year
Financial Accounting |  | GT | Create Reorganization | Create Reorganization for new period in Production and Sandbox (Ex. 202307 - July FY24) @8PM - After finops email gives clearance | Saturday | 2023-07-01 | Complete | Tyler Dixon Yongmei Zhang | Done the last working day of the month usually will continue month for future periods.
Financial Accounting |  | GT | Deadline - Accounting Journals to Equipment Ledger Accounts for Sponsored Projects | Deadline for all FY2023 journal entries to equipment accounts for sponsored projects | Saturday | 2023-07-01 | Complete | Denise Hairston Kelly McArthur Josh Rosenberg Julie McCoy |  | RI: We can mark this deadline as complete. | Tyler to mark as completed when deadline approaches. Per Kelly at 6/27 meeting: this will be done before Grants and GTRI cose. New date 7/1.
Bursar/Treasury |  | GT | Verify Deferred Summer Term Revenue | Verify Deferred Summer Term Revenue Split for next FY | Saturday | 2023-07-01 | Complete | Gloria Kobus Jim Pierce Gloria Kobus | Send to Controller & Associate Controller | Send to Controller & Associate Controller
Integrations |  | GT | Change Automated Schedule to Manual for any FY23 Integrations from 6/26 until 7/4 | Auto loads need to be held until we have opened for FY23 (Banner, Payroll, Commitment Accounting, etc.). Automated schedule starts back on Wednesday, July 5th | Saturday | 2023-07-01 | Complete | Chhaya Amin Timothy Hughes Yongmei Zhang Tyler Dixon Serena Simpson |  | 6/30/22 - Had a meeting with Finops, EADI, Controller; confirm with Chhaya
Financial Accounting |  | GT/ATHL | Review ledger for transactions posted in FY23 with a budget ref of BR24 | Review ledger for transactions posted in FY23 with a budget ref of BR24 at mid-day and end of day, each day through closeout to ensure transactions are not posting to the ledger with the wrong budget reference worktag. | Saturday | 2023-07-01 | Ongoing | Yongmei Zhang Tyler Dixon | Ongoing through Year-End
Financial Accounting | FDM1 | GT/ATHL | FDM1 - Update Driver Worktags with new CY Budget Ref (BR24) (In Production and Sandbox) | FDM2 - Update Driver Worktags with new CY Budget Ref (BR24) - FY24 period will be open for this task. (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Yongmei Zhang Tyler Dixon Serena Simpson |  | This step must be done before FDMTEST can begin; Teams message will be sent to group when this has been completed 6/29/2022 - This has been delayed to Saturday. | (This process requires more bandwidth) PROCESS WILL START @ 9:30AM; ALL COMMUNICATIONS WILL BE IN TEAMS CHAT WHEN COMPLETED
Grants | FDM6 | GT | Update Award Lines - Budget Reference (worktags) (In Production and Sandbox) | Update Award Lines - Budget Reference (worktags) (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Amy Zhang Tony Wang Neli Tranakiev |  | Wait on FSM to add BR23 to Workday. Must confirm with FSM team when to begin. 6/30/2022 - Has to happen after hours 07/01/2022 -This will be done Saturday (2nd) | After FSM to update driver worktage to (BR24) . approximately 2 hours
Financial Accounting | FDM2 | GT/ATHL | FDM2 - Update Custom Validation for BR24 PCARD by adding the prior year BR to the validation (In Production and Sandbox) | PCARD CONDITION RULE: 1) CONDITION RULE: BUDGET REFERENCE ON PCARD MUST BE CURRENT YEAR (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Daniel Stewart Sabrena Nettles Yongmei Zhang Tyler Dixon |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 6/30/2022 - Has to happen after hours 07/01/2022 | Daniel Stewart and Sabrena Nettles will volunteer to support FY23 YE task. Chris Cho has volunteered to support YE for nex year.
Financial Accounting | FDM3 | GT/ATHL | FDM3 - Update Custom Validation for (BR24) Expense Report (In Production and Sandbox) | EXPENSE REPORTS CONDITION RULE: 1) CONDITION RULE: The budget reference on expense report must be equal to current fiscal year (example: FY23/BR23). 2) CONDITION RULE: Expense Report Date on the header section should be within the same fiscal year (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Daniel Stewart Sabrena Nettles Yongmei Zhang Tyler Dixon |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 6/30/2022 - Has to happen after hours 07/01/2022 | Daniel Stewart and Sabrena Nettles will volunteer to support FY23 YE task. Chris Cho has volunteered to support YE for nex year.
Financial Accoutning | FDM4 | GT/ATHL | FDM4 - Update Custom Validation for (BR24) Accounting journal (In Production and Sandbox) | ACCOUNTING JOURNAL EVENT/ACCOUNTING JOURNAL UNPOST-REVERSE EVENT CONDITION RULE: 1) CONDITION RULE: BUDGET REFERENCE WORKTAG IS NOT EQUAL TO CURRENT YEAR ACCOUNTING ADJUSTMENT EVENT: 2) CONDITION RULE: CURRENT BUDGET DATE ON ACCOUNTING ADJUSTMENTS IS PY? (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Daniel Stewart Sabrena Nettles Yongmei Zhang Tyler Dixon |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 6/30/2022 - Has to happen after hours 07/01/2022 | Daniel Stewart and Sabrena Nettles will volunteer to support FY23 YE task. Chris Cho has volunteered to support YE for nex year.
Financial Accoutning | FDM5 | GT/ATHL | FDM5 - Update Custom Validation for (BR24) Freight (In Production and Sandbox) | Condition Rule: 1) Add Freight to New Line (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Daniel Stewart Sabrena Nettles Yongmei Zhang Tyler Dixon |  | Per Carol: This has been completed for FY23 (only need to review) 7/1/22 - N/A the validation was changed. This may drop off next year. | Daniel Stewart and Sabrena Nettles will volunteer to support FY23 YE task. Chris Cho has volunteered to support YE for nex year.
Financial Accounting | FDM2A | GT/ATHL | FDM2A – Update PCARD Account Posting Rule (In Production and Sandbox) | Account Posting Rule: Spend Resulting Ledger Account: 714900: Purchase Card Expense Add BR24 (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Yongmei Zhang Tyler Dixon |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 6/30/2022 - Has to happen after hours 07/01/2022
Security | FDM7 | GT/ATHL | Add Expense Analyst role back to Expense Report and Spend Authorization Initialization BPs steps so PBS can test the new Budget Reference | Add Add security roles from Business Process policy Initiation Steps so PBS can test the new Budget Reference Initiating Action BP: Create Spend Authorization - Role: Expense Anlayst Initiating Action BP: Create Spend Authorization for Worker - Role: Expense Analyst Initiating Action BP: Create Expense Report - Role: Expense Anlayst | Saturday | 2023-07-01 | N/A | Marvin Petty Ruby Hollender | Roles: Expense Analyst BPs: Expense Report Event and Spend Authorization | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start .07/01 - completed per request by MB
Grants |  | GT/ATHL | Reporting to Team to change Budget Reference Default on Reports has been updated to the new fiscal year budget reference (In Production and Sandbox) | Verify with Deepthi and the Reporting Team that the Budget Reference for reports have been updated to default the current Budget Reference for the new fiscal year (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Yongmei Zhang Tyler Dixon Nate Watkins Deepthi VenReddy |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 6/30/2022 - Has to happen after hours 07/01/2022 | JIRA wkdya-8497, Financial & FDM reports are updated in GT7. Deepthi will update these reports in 07/01/2023 in PROD. Covid Expense reports will have to be done after Richard updates Budget Structure to FY24. (Added new task on prod list)
Security |  | GT/ATHL | Restore all Security for Central and Campus roles in Sandbox only | Restore all Security roles for Central and Campus in Sandbox only | Saturday | 2023-07-01 | Complete | Marvin Petty Ruby Hollender
Financial Accounting |  | GT/ATHL | Update Workday Financials Operating Ledger Open for FY2024 (In Production and Sandbox) | Update Workday Financials Operating Ledger Open for FY2024 – Expenses, Financial Accounting, Grants, PCard, Procurement, Supplier Accounts, etc. Transactions entered will post to the ledger in FY24. (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Tyler Dixon Yongmei Zhang | 11 or 6 | 7/5/2022 - See YE Communications Folder for email; ADD: controller@business.gatech.edu
Financial Accounting | FDMTEST1 | GT/ATHL | Update Driver Worktags with new Budget Ref (BR24) (In Production and Sandbox) | Run processes to update driver worktags with new Budget Reference (BR24) (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Yongmei Zhang Tyler Dixon Serena Simpson |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 7/2/22 - Can begin @1:ooPM | Duplicate
Financial Accounting | FDMTEST2 | GT/ATHL | Create Online Journals and Accounting Adjs to test update Driver Worktags with new CY Budget Ref (BR24) (In Production and Sandbox) | Create Journals, Accounting Adjustment (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Yongmei Zhang Tyler Dixon Serena Simpson | CON_20210702_01 | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 7/2/22 - Can begin @1:ooPM
Expenses | FDMTEST3 | GT | Create Expense Reports to test update to Driver Worktags with new CY Budget Ref (BR24) (In Production and Sandbox) | Create Expense Reports (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Laura Jamison Jennifer Jacobs |  | 7/2/22 - Annette tested. BR populated. Expense Rpt EXP-1097799 received budget check error. Apparently the accounting period is not open. | 6/29/23: TEST in PROD - we have rights. 7/1/23- Testing completed and sucessful -JJ
Expenses | FDMTEST4 | ATHL | Create Expense Reports to test update to Driver Worktags with new CY Budget Ref (BR24) (In Production and Sandbox) | Create Expense Reports (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Selinda Biggers |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 07/01/22 - Per MB Annette Ross is completing this Saturday (early) 7/2/22 - Can begin @1:ooPM | 7/1-EXP-1146988 - In PROD
ATHL | FDMTEST6 | ATHL | Create Requisitions to test update Driver Worktags with new CY Budget Ref (BR24) (In Production and Sandbox) | Create Requisitions (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Selinda Biggers Whitney Tate Erin Mitchell Daniel Stewart |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 7/2/22 - Can begin @1:ooPM | 7/1 - ARQ-100394 - IN PROD
Procurement | FDMTEST7 | GT | Create Requisitions to test update Driver Worktags with new CY Budget Ref (BR24) (In Production and Sandbox) | Create Requisitions (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Nazneen Keen Michael Barnwell Whitney Tate Erin Mitchell Daniel Stewart |  |  | TEST IN PROD: Notes: We cannot "complete" the process, we just initiate and enter a driver worktag to ensure that the BR24 populates and when we click SUBMIT it has a process definition error
Supplier Accounts | FDMTEST9 | GT | Create Supplier Invoice Requests to test update Driver Worktags with new CY Budget Ref (BR24) (Sandbox only) | Create Supplier Invoice Request (Sandbox only) | Saturday | 2023-07-01 | Complete | Laura Jamison Whitney Tate Daniel Stewart | 7/6/2021: Sending error message to GL Prod Supp | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 7/2/22 - Can begin @1:ooPM | Test in Sandbox after security - Note: We do NOT test supplier invoices because it follows the BR of the PO's.
Supplier Accounts | FDMTEST10 | ATHL | Create Supplier Invoice Requests to test update Driver Worktags with new CY Budget Ref (BR24) (Sandbox only) | Create Supplier Invoice Request (Sandbox only) | Saturday | 2023-07-01 | Complete | Selinda Biggers Daniel Stewart |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 7/2/22 - Can begin @1:ooPM | INVRQST-052423 - In Sandbox
Procurement | FDMTEST8 | GT | Create PO's to test update Driver Worktags with new CY Budget Ref (BR24) (Sandbox only) | Create Purchase Orders (Sandbox only) | Saturday | 2023-07-01 | Complete | Michael Barnwell Whitney Tate Erin Mitchell Daniel Stewart |  | 7/2/22 - This needs to be evaluated next year to anticipate testing in Sandbox due to approval processes | The only way we can test this in prod is Create Purchase Order (after security is enabled) in the search bar, which is actually not our standard procedure. We will test in sandbox by approving a requisition until it becomes a purchase order.
ATHL | FDMTEST11 | ATHL | Create PO's to test update Driver Worktags with new CY Budget Ref (BR24) (Sandbox only) | Create PO's (Sandbox only) | Saturday | 2023-07-01 | Complete | Selinda Biggers Whitney Tate Erin Mitchell Daniel Stewart |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 7/2/22 - This needs to be evaluated next year to anticipate testing in Sandbox due to approval processes | The only way we can test this in prod is Create Purchase Order (after security is enabled) in the search bar, which is actually not our standard procedure. We will test in sandbox by approving a requisition until it becomes a purchase order. 7/1 - APO-100340 - In SandBox
Banking | FDMTEST13 | ATHL | Create Ad Hoc Bank Transactions to test update Driver Worktags with new CY Budget Ref (BR24) (In Production and Sandbox) | Create Ad Hoc Bank Transactions (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Selinda Biggers | 7/6/21 - Will be completed tomorrow | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 7/2/22 - Can begin @1:ooPM | 7/1-AHBT-111040 - In PROD
Expenses | FDMTEST14 | GT | Create Spend Authorizations to test update to Driver Worktags with new CY Budget Ref (BR24) (In Production and Sandbox) | Create Spend Authorizations - (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Laura Jamison Jennifer Jacobs |  | 7/2/22 - Annette tested. BR populated. Spend Auth AUTH-1041450 received budget check error. Apparently the accounting period is not open. | 6/29/23: TEST in PROD - we have rights. 7/1/23- Testing completed and sucessful -JJ
Expenses | FDMTEST15 | ATHL | Create Spend Authorizations to test update to Driver Worktags with new CY Budget Ref (BR24) (In Production and Sandbox) | Create Spend Authorizations - (In Production and Sandbox) | Saturday | 2023-07-01 | Complete | Selinda Biggers |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 07/01/22 - Per MB Annette Ross is completing this Saturday (early). 7/2/22 - Can begin @1:ooPM | 7/1 - AUTH-1065316 - In PROD
Banking | FDMTEST12 | GT | Create Ad Hoc Bank Transactions to test update Driver Worktags with new CY Budget Ref (BR24) | Create Ad Hoc Bank Transactions - This can only be done when new Fiscal Year is open | Saturday | 2023-07-01 | Complete | Tammy Putnal |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 7/2/22 - Can begin @1:ooPM
Financial Accounting |  | GT | Update Ledger Period Status to FY23-JUN Close in Progress: Everything except: Customer Accounts & Banking (12pm) | Update Ledger Period Status to FY23-JUN Close in Progress: Everything except: Customer Accounts & Banking (12pm) Open Activities: Customer Accounts & Banking Closed Activities: Journals, Expenses, Operational Accounting, Procurement, Accounting Adjustments, Accounting Center Summary Journals, Assets, Deferred Cost, Equity Pickup, Journals Netting Transaction, Non-Controlling Interest, Unused Features | Saturday | 2023-07-01 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson
Expenses |  | GT | Load Spend Authorizations for travel 4/30 and later into Workday as an Approved Commitment | Fully approved Spend Authorizations with travel dates of 4/30 or later will be loaded & committed in FY24 by 7/3. Ensure Ledger Account for Reserve for Commitments for FY2024 is 381104 in ledger posting rules | Sunday | 2023-07-02 | Complete | Laura Jamison Jennifer Jacobs Michael Barnwell Nate Watkins | 7/6/21- In progress and should be completed today | 07/04/22: Loaded successfully.
Banking |  | GT | Change Ad Hoc Bank Transaction Template | Change all Ad hoc bank transaction templates that use Budget Ref after the Budget Ref is updated, before the templates are used in the new fiscal year. The AHBT templates do not automatically change the Budget Ref to the following year and must be changed manually. | Monday | 2023-07-03 | Complete | Tammy Putnal | 7/6/21- In progress and should be completed today | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 7/2/22 - Can begin @1:ooPM
Security | SEC06u | GT/ATHL | CENTRAL - Supplier Invoices OPEN for FY24 ADD BACK Security for Supplier Invoice Event | Add Back central office security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 8AM) | Monday | 2023-07-03 | Complete | Marvin Petty Tray Mathis Sabrena Nettles Laura Jamison
Security | SEC06i | ATHL | CENTRAL - GTAA Purchase Order Event OPEN for FY24 ADD BACK Security for GTAA Purchase Order Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@8AM) Role: Buyer | Monday | 2023-07-03 | Complete | Marvin Petty Daniel Stewart Selinda Biggers Whitney Tate
Security | SEC06h | GT | CENTRAL OFFICE - Purchase Order Event (Default Definition) OPEN for FY24 ADD BACK Security for Purchase Order Event (Default Definition) | Add back to initiation for Business Process Policy - Buyer - Change Order Buyer - 500K Buyer - GTRI Buyer - GTRI Coordinator 10K Buyer - Intermediate 150K Buyer - Low 75K Buyer - Purchasing Coordinator - 10K Buyer - Senior Buyer - 250K Buyer - Purchasing Coordinator - 25K (@8AM) | Monday | 2023-07-03 | Complete | Marvin Petty Daniel Stewart Erin Mitchell Whitney Tate | Removed Procurement Manager Procurement Director Added: Purchasing Coordinator - 25K per Ruby Hollender
PCard | FDMTEST5 | GT | Create PCard Verifications to test update Driver Worktags with new CY Budget Ref (BR24) | Create PCard Verifications - This can only be tested when open for the new Fiscal Year | Monday | 2023-07-03 | Complete | Whittney Haynes |  | Per Whitney Tate: For P-Card BR23 testing - Hi! There is no way to test the PCV as we have to be one of the cardholders. We will look at it on Tuesday morning. We will make sure we have a pending one next year. Sorry for the oversight. | Passed the test - Please note that we have to wait until Workday reopens to test this as no pending transactions can be open at year end.
Financial Accounting |  | GT | Final Journal Entries for Auxiliary Services Finance | Auxiliary Services Finance Closing journal entries due | Monday | 2023-07-03 | Complete | Barbara Hanschke Brian Cochran - Sharon Ahmed | 7/6/21 - Anticipate completing today | Brian would like to post first week of July. This date should not be moved for next year. FSM team will post this Journal 06.24.2022. we plan on submitting a JE prior to June 30th to liquidate unspent but Amy has been consulted | Should be Sharon Ahmed
Security | SEC06w | GT | Supplier PORTAL OPEN for submitting invoices for FY2024 ADD BACK Access for Supplier PORTAL for submitting invoices | Supplier PORTAL OPEN for submitting invoices for FY2024 ADD BACK Access for Supplier PORTAL for submitting invoices Supplier Contract As Self on the Supplier Invoice BP (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Chhaya Amin David Adcock | It is very important that this task is completed in FY22; this probably needs to be shut down the day before final AP payments
Grants |  | GT | Post Final GSTRP for Cost Share Grants | EIB to post final GSTRP expense to Grants - Must be completed after final Commitment Accounting entries are posted to EDW. | Monday | 2023-07-03 | Complete | Justin Yoo Jonathan Jeffries |  |  | Verify Justin has correct year-end access to process EIB . Terryl lets jonathon know the EDW refresh is completed, Justin then proceeds EIB. GCA_20230630_01
Payroll |  | GT | Manager Self-Service (MSS) transactions Due - Biweekly Pay Period Ending 7/08 | Manager Self-Service (MSS) transactions for employee payroll actions due - Biweekly pay period ending 7/08 | Monday | 2023-07-03 | Complete | Jerri Phillips
Assets |  | GT | GSFIC FY23 MRR Reports – Confirm with | GSFIC FY23 MRR Reports – Confirm with | Monday | 2023-07-03 | Complete | Avni Patel Denise Hairston
Bursar/Treasury |  | GT | Refund Clearing Account | Confirm account 219852 is reconciled | Monday | 2023-07-03 | Complete | Xin Mu Gloria Kobus | 7/19/21 - Still in Progress | 7/5/22 - Gloria Kobus will get back to FSM about altering this task. 7/6/22 - Due to the USG on the 29th of July 7/7/22 For FY23 this task needs to be moved to a 7/7 deadline
Grants |  | GT | Deadline - Grant Budget Amendments by Organization | Deadline to submit Grant Budget Amendments by Org in Workday | Monday | 2023-07-03 | N/A | Josh Rosenberg Glen Campopiano |  | Per Doug, The analyst team is not moving any budgets. The "budget amendment for organization" is a process done at the department level and Grants is not involved in the approval process. It's just a deadline. | No need to monitor Grants deadline, bc they do not have their security removed anymore.
Procurement |  | GT/ATHL | First Day for FY2024 Requisitions entry | FY2024 requisitions can be entered into Workday | Monday | 2023-07-03 | Complete | Erin Mitchell
Security | SEC06 | GT/ATHL | CAMPUS - Supplier Invoice Requests OPEN for FY24 ADD BACK Security to Supplier Invoice Request Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Laura Jamison Yongmei Zhang Tyler Dixon | Roles: Employee As-Self; Contingent Worker As-Self; Unit Receipt Creator BPs: Supplier Invoice Request Event
Business Assets | SEC06a | GT | Property Control should start reveiwing Trackable Lines for Supplier Invoices for Supplier Payments | Property Control should start reviewing Trackable Lines for supplier invoices that affect assets to ensure the payments can be made to suppliers These transations hit the Common Book in the new fiscal year. Property Control should not Register Assets until Business Assets is open for the new fiscal year. They will be notified about this by the Controller's Office team. | Monday | 2023-07-03 | Ongoing | Frederick Trotter Tanisha Tigner Kelly MacArthur | New for FY22 YE Close | 7/6/22 - FT will take care of this task and circle back.
Security | SEC06b | GT/ATHL | CAMPUS - Expense Reports OPEN for FY24 ADD BACK Security for Expense Report Event | Add Back Campus Security Groups from Expenses Transaction Business Process Policy Initiation Steps so campus can enter transactions. Add back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. Initiating Action BP: Create Expense Report - Role: Employee as-self Initiating Action BP: Create Expense Report for Worker - Role: Expense Preparer Initiating Action BP: Create Expense Report for Non-Worker - Role: Expense Preparer Add back ability for ‘Employee as Self’ and 'Expense Preparers' to copy Expense Reports. Add back all access from Expense Preparer. See 'View Security for Securable Item' for the 'Copy Expense Report' task. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Laura Jamison Yongmei Zhang Tyler Dixon | Roles: Employee as Self; Contingent Worker as-self, Expense Preparer BPs: Expense Report Event | 7/1/22 - Per MB Annette will test this Saturday Morning.
Security | SEC06c | GT/ATHL | CAMPUS - Requisitions OPEN for FY24 ADD BACK Security for Requisition Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Ruby Hollender Whitney Tate | Role: Employee As-Self; RQ Reviewer
Security | SEC06c1 | GT/ATHL | CAMPUS - Requisitions OPEN for FY24 ADD BACK - Security for Requisition Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) BP: Requisition Initiating Action: Check-Out Add: Employee-As-Self, RQ Reviewer | Monday | 2023-07-03 | Complete | Marvin Petty Ruby Hollender Whitney Tate Michael Barnwell Daniel Stewart
Security | SEC06d | GT/ATHL | CAMPUS - Requisitions OPEN for FY24 ADD BACK Security for Requisition Event | Requisitions closed from 4pm on 6/22 until 9am on 7/3 - Add back Campus Security Groups from Requisitions Business Process Policy Initiation Steps so campus can enter transactions. (@ 9AM) Add back to Review and Approve BP policy Action Step: Review Requisition *Cost Center Manager *Management Chain *Manager *Requisition Requester *RQ Reviewer *Top Level Manager's Approver Action Step: Approve *Business Asset Accountant - Equipment *Business Asset Accountant - Non-Equipment *Business Asset Manager *Business Asset Surplus Manager *Cost Center Manager *Custodial Entity Manager *Designated Manager *Design Manager *Environmental Health & Safety *Gift Manager *Gift Portfolio Manager *Grant Manager *GTAA CFO *GTAA Compliance Group *GTAA - Equipment Manager *GTRI Business Asset Surplus Manager *GTRI Charge Code Manager *Manager *OM Manager *Primary Requestor Contact *Project Manager *Project Master *Top Level Manager's Approver | Monday | 2023-07-03 | Complete | Marvin Petty Yongmei Zhang Tyler Dixon Erin Mitchell Whitney Tate
Security | SEC06e | GT/ATHL | CAMPUS - Spend Authorizations OPEN for FY24 ADD BACK Security for Spend Authorization Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Laura Jamison Yongmei Zhang Tyler Dixon Serena Simpson | Roles: Employee as Self; Contingent Worker as-self, Expense Preparer BPs: Spend Authorization Event
Security | SEC06f | GT/ATHL | CAMPUS - Receipts (Supplier Accounts) OPEN for FY2024– Campus ADD BACK Security for Receipt Creator | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. Receipt Creator. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Laura Jamison Yongmei Zhang Tyler Dixon | Roles: Employee As-Self; Contingent Worker As-Self; Unit Receipt Creator Receipt Creator BPs: Receipt
Security | SEC06g | GT | CAMPUS - Procurement Card Transaction Verifications OPEN for FY2024 - Campus ADD BACK Security for Procurement Card Transaction Verification Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Daniel Stewart Whittney Haynes | Roles: Employee As-Self BPs: Procurement Card Transaction Verification Event
Security | SEC056j | GT | CAMPUS - Facilities Purchase Order Event OPEN for Facilities for FY2024 ADD BACK Security for Purchase Order Event (Facilities) | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) Role: Facilities Contract Buyer | Monday | 2023-07-03 | Complete | Marvin Petty Daniel Stewart Erin Mitchell Whitney Tate
Security | SEC06k | GT | CAMPUS - Purchase Order Event (Subaward) OPEN for FY24 ADD BACK Security for Purchase Order Event (Subaward) | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) Role: Subaward - Contracts Specialist | Monday | 2023-07-03 | Complete | Marvin Petty Daniel Stewart Erin Mitchell Whitney Tate
Security | SEC06k | GT | ADD BACK Shopping Access in Jaggaer | Whitney Tate turns on permissions to shopping tasks in Jaggaer on RQ Reviewer, GTRI Transaction View and Employee as Self. | Monday | 2023-07-03 | Complete | Whitney Tate | Per Michael Barnwell, changed date from 25th to the 18th.
Security | SEC06l | GT/ATHL | CAMPUS - Supplier Invoice Event OPEN for FY24 ADD BACK Security for Supplier Invoice Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Tray Mathis Sabrena Nettles Laura Jamison | Roles:Facilities Invoice Data Entry Specialist; Payroll Invoice Data Entry Specialist; OSP Invoice Data Entry Specialist; Account Payable Data Entry Specialist BP:Supplier Invoice Event
Security | SEC06m | GT | CAMPUS - Supplier Contract Event OPEN for FY24 ADD BACK Security for Supplier Contract Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Erin Mitchell Daniel Stewart | Roles: Real Estate Contract Specialist BPs: Supplier Contract Event
Security | SEC06n | GT | CAMPUS - Supplier Contract Amendments OPEN for FY24 ADD BACK Security fro Supplier Contract Amendment Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Erin Mitchell Daniel Stewart | Roles: Real Estate Contract Specialist BPs: Supplier Contract Amendment Event
Security | SEC06o | GT/ATHL | CAMPUS - Budget Amendments for Projects OPEN for FY24 ADD BACK Security for Budget Amendment Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Maurena Maynor Doug Feller Josh Rosenberg | Roles: Cost Center Manager, Gift Manager, Grants Manager, Grants Budget Amendment Creator, Project Master BPs: Budget Amendment Event
Security | SEC06p | GT/ATHL | CAMPUS - Accounting Journals OPEN for FY24 ADD BACK Security for Accounting Journal Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Yongmei Zhang Tyler Dixon Serena Simpson | Roles: Accountant; Accountant - Campus Service Center; Accountant - Central Business Office BPs: Accounting Journal Event;
Security | SEC05a | GT/ATHL | CAMPUS - Accounting Journal Adjustments OPEN for FY24 ADD BACK Security for Accounting Adjustment Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Tingler Annie Davis Serena Simpson Daniel Stewart
Security | SEC06r | GT/ATHL | CAMPUS - Accounting Journal Unpost/Reverse OPEN for FY24 ADD BACK for Accounting Journal Unpost-Reverse Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Yongmei Zhang Tyler Dixon Serena Simpson | Roles: Accountant BPs: Accounting Journal Unpost-Reverse Event
Security | SEC06s | GT/ATHL | CAMPUS - Accounting Copy Journal Action OPEN for FY24 ADD BACK for Copy Journal Action | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-03 | Complete | Marvin Petty Yongmei Zhang Tyler Dixon Serena Simpson | Roles: Accountant Actions: Copy Journal Action
Security | SEC06v | GT/ATHL | Ad Hoc Payments OPEN for FY24 ADD BACK Security for Ad Hoc Payment Event | Add Back campus security roles from Business Process Policy Initiation Steps users can enter transactions. (@ 9AM) ROLES: Accounts Payable Accountant Accounts Payable Data Entry Specialist Bursar Cash Manager Bursar Cash Specialist Cash Manager Facilities Invoice Data Entry Specialist OSP Invoice Data Entry Specialist PE Cashier PE Cash Manager Accounts Payable Analyst | Monday | 2023-07-03 | Complete | Marvin Petty Laura Jamison Leanne Sheffield Selinda Biggers | Roles: Accounts Payable Accountant Accounts Payable Data Entry Specialist Bursar Cash Manager Bursar Cash Specialist Cash Manager Facilities Invoice Data Entry Specialist OSP Invoice Data Entry Specialist PE Cashier PE Cash Manager Accounts Payable Analyst
Financial Accounting |  | GT | Add Back Spend Authorization critical Custom Validation called 'Justification Required for Late Travel'. | Add Back Spend Authorization critical Custom Validation called 'Justification Required for Late Travel'. This can occur anytime after the Load of Spend Authorizations is complete. | Monday | 2023-07-03 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson
Financial Accounting |  | GT/ATHL | Send Email to Campus that Workday Financials Operating Ledger Open for FY2024 @9AM | Send Email to Campus Workday Financials Operating Ledger Open for FY2024 – Expenses, Financial Accounting, Grants, PCard, Procurement, Supplier Accounts, etc. Transactions entered will post to the ledger in FY24. **Send email to Campus that FY24 is open. (fin-all from the noreply Controller's Office email) | Monday | 2023-07-03 | Complete | Tyler Dixon Yongmei Zhang | 11 or 6 | 7/5/2022 - See YE Communications Folder for email; ADD: controller@business.gatech.edu
Financial Accounting |  | GT/ATHL | Remove Year-End Closeout Message from Workday | Remove Message - "Workday FIN Down from Wednesday, June 28 at 5PM until Monday, July 3 at 9AM to facilitate Year-End Close" - Link to Grid on Controller's Office Year End Page | Monday | 2023-07-03 | Complete | Chhaya Amin Michael McCoy Timothy Hughes David Adcock Yongmei Zhang Tyler Dixon
Financial Accounting |  | GT/ATHL | Remove Year-End Closeout Message from Techworks | Remove Message - "Workday FIN Down from Thursday, June 28 at 5PM until Tuesday, July 5 at 9AM to facilitate Year-End Close" - Link to Grid on Controller's Office Year End Page - Follow up on Incident ServiceNow ticket | Monday | 2023-07-03 | Complete | John Gisi Yongmei Zhang Tyler Dixon Serena Simpson David Adcock | 7/06/21 - Will be completed tonight 7/7/21 - Will be completed today (this is a change not a removal) /8/21 - Should be completed today | 7/5/2022 - John is working on this
Business Assets |  | GT/ATHL | Final Asset Registrations for FY2023 | Complete processing for asset registration for FY2023 | Monday | 2023-07-03 | Complete | Frederick Trotter Tanisha Tigner Selinda Biggers Tia Randolph | 7/6/21: Should be completed today; 7/7/21: Still finalizing | 7/7/22: Per Selinda there might be asset to register. She will circle back with Serena 7/8/22: Per Selinda has not been completed, will circle back on status. 7/11/22 - Athletics is not closed. This will not effect YE close for FY22 | 7/5/23 - Selinda: This may be completed Friday. Assets Team: Will meet later today to discuss
Business Assets |  | GT | Final Asset Management Equipment Adjustments | Make all final adjustments to Assets in the Workday system - CAPITAL LEDGER | Monday | 2023-07-03 | Complete | Frederick Trotter Tanisha Tigner Denise Hairston Avni Patel Regina Wilson Kelly MacArthur | 7/6/21: Should be completed today | 7/6/22 - KM Still working on this and hopefully will be completed today 7/8/22 - KM Will have an adjustment today.
Security | SEC03f | GT | CAMPUS - Budget Amendments for Gifts CLOSED for FY23 REMOVE Security for Budget Amendment Event | Remove campus security roles from Business Process Policy Initiation Steps so users cannot enter transactions. (@ 5PM) | Monday | 2023-07-03 | Complete | Marvin Petty Maurena Maynor Antinina Wilkerson Nate Watkins Doug Feller Josh Rosenberg | Roles: Cost Center Manager, Gift Manager, Grants Manager, Grants Budget Amendment Creator, Project Master BPs: Budget Amendment Event |  | Per a meeting on 6/26 with Budget Office, GTF, and GTRC: the gift budget amendment security will be removed on July 3rd, and will be added back on the 11th after the carry forward budget is complete.
Pcard |  | GT | FY24 - PCard Transaction Load - 6/16 to 6/30 | Load transactions from 6/16 to 6/30 in Workday (Load in FY24) - Posted on the first working day of the month | Monday | 2023-07-03 | Complete | Whittney Haynes Mike McCoy Timothy Hughes Chhaya Amin | 7/6/21 - Should be completed today | 7/6/2022 - WH meeting with BOA for missing transactions for the 17th. This has been escalated within BOA. June 18th – June 30th have been successfully added to Workday and cardholders have started the reconciliation process. Anticipate a meeting today with BOA 7/8/22 - Per Whittney BOA is waiting to confirm transactions from post date of June 17th with Visa. Once this is completed we will be sent to file. 7/11/22 - This JE is for FY23. This will not effect YE close for FY22 | 7/5/23 - Done on the first working day of the month.
OIT |  | GT | ServiceNow GTPE Course Section Request add back | ServiceNow GTPE Course Section Request add back | Monday | 2023-07-03 | Complete | Alex Agle Alpha Team (Service Now Support Group) Erik Powell vdarapu3 Tyler Dixon Yongmei Zhang |  |  | This task is for FY24. This year Yongmei will send an email to Lamar Handy and ask him to stop adding GTPE Projects on June 30th. He can start again when we open for July 3, 2023. (Process next year is to put in a ServiceNow ticket)
Commitment Accounting | COMM1 | GT | Final Commitment Accounting Journals for FY2023 (EDR & FRF) | Final Commitment Accounting Journals for FY2023 (EDR & FRF) | Wednesday | 2023-07-05 | Complete | Terryl Barnes Jason Cole Anagha Sahasrabudhe Chhaya Amin | 7/2/2021: Completed | NOTE: EDW MUST BE REFRESHED; THIS HAS TO BE CONFIRMED BEFORE GTRI CAN START WITH THEIR HPOST AND QPOST; 7/2/2 - Files posted in BR23 by mistake (Header for file was capitalized for Budget Reference) CMR_20220630_03 CMR_20220630_04 EDR_20220630_06 FRF_20220630_04
|  | GT | EDW Refresh | EDW Refresh - This must be done before GTRI can start with their hpost and qpost and after commitment accounting journals posted | Wednesday | 2023-07-05 | Complete | Arun Baskaran Nick Chaviano Terryl Barnes Yongmei Zhang Serena Simpson
Commitment Accounting |  | GT | BWACC3 - Generate Transactions and Provide Biweekly Payroll Accrual REVERSAL EIB File to Workday/Financial Accounting to post in FY2024/BR24 | Generate Transactions and Provide Biweekly Payroll Accrual REVERSAL EIB File to Workday/Financial Accounting to post in FY2024 | Wednesday | 2023-07-05 | Complete | Terryl Barnes Jason Cole Anagha Sahasrabudhe | 7/6/21- In progress and should be completed today; EDR_20210701_01 and FRF_20210701_01 | 7/5/2022: Process in OneUSG today. Workday will reflect tomorrow 7/6/22
Financial Accounting |  | GT | Analyze Lapsed Orders and Receivable Write Off's for Fund Balance | Analyze Lapsed Orders and Receivable Write Off's for Fund Balance - Provide worksheet with beginning fund balance, lapsed orders, and receivable write off's to fund balance accounts. | Wednesday | 2023-07-05 | Complete | Maurena Maynor Lee Waites Controller's Office | 6/29/21 - Maurena will talk to Lee 6/30/21 - This will be completed 07/01 | 6/28/22 - Waiting on Workday fix can not proceed. 6/30/22- This can be completed Friday 07/01/2022; 7/5/22 - This task is being worked on now. This is not done till July. We will need to re-visit due date for this task. 7/6/22 - Per Maurena, this will completed at the end of the week.
Financial Accounting |  | GT | Verify: BWACC4 - Post Biweekly Payroll Accrual REVERSAL EIB File (EDR) to post in FY2024/BR24 | Verify (EADI Development team was able to load and post journals) BWACC2 - Post Biweekly Payroll Accrual REVERSAL EIB File (EDR) to the Ledger | Wednesday | 2023-07-05 | Complete | Yongmei Zhang Tyler Dixon | 7/6/21 - Commitment Accounting must be open; should b completed today; EDR_20210701_01 and FRF_20210701_01 | 7/5/22 - Will verify it is in Workday tommorrow. 7/6/22 - EDR_20220702_01 FRF_20220702_01
Financial Accounting |  | GT | Georgia Tech Professional Education (GTPE) Close | Georgia Tech Professional Education (GTPE) Close | Wednesday | 2023-07-05 | Complete | Latanya Buckner Tony Yusan | * must be on-call for closing issues | * must be on-call for closing issues 7/5/22 - Will post last journal at 5:30PM
Financial Accounting |  | GT | Inventory Adjustment for Supply Stores | Mark down inventory for year end. Physical Plant, Pharmacy, Housing and Post Office - End of year balance should be inventory for each quarter divided by four. | Wednesday | 2023-07-05 | Complete | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur | 7/6/21 - Use BR21
Financial Accounting |  | GT | OPB Revenue, Expenditure, and Transfer Request | OPB Revenue, Expenditure, and Transfer Request - this is a monthly task and does not effect close in any way. Just a reporting requirement. | Wednesday | 2023-07-05 | Complete | Chris Drummond Amry Stanley
Grants |  | GT | Process Journal to Post Fringe Benefit Reductions | Process JE to post the fringe benefit reduction by function for over recovery | Wednesday | 2023-07-05 | Complete | Josh Rosenberg Jonathon Jeffries | 7/6/21 - Should be completed today 7/7/21 - Amy will check with Jonathon | GCA_20220630_02 | This will be completed after GTRI completing a final JE and the payroll allocation process is complete. GCA_20230630_02 GCA_20230630_04
Financial Accounting |  | GT | Prepare report of accounts receivable write-offs | Send report and supporting documentation to State Accounting Office | Wednesday | 2023-07-05 | N/A | Gloria Kobus | 7/8/21 - Still in progress. Working on revisions | 7/7/22 - Per Gloria: It was sent and apporved and the write offs occurred on 6/29
Business Assets |  | GT | Post Capital Journal Entry to write off Missing Year 1 Equipment Assets | Do Capital journal entry (EIB) to write off Missing Year 1 assets | Wednesday | 2023-07-05 | Complete | Regina Wilson Denise Hairston | 7/7/21 - EIB was submitted today |  | FSM team need lifte custom validation - Fund - Use of the Restricted - Foundation Fund Code REQUIRES a Designated and Gift worktag. Regina will send FSM email to support the worktag: "Designated:DE00002328 Equipment Gifts - Equipment Gifts - Federal" does not allow worktag values: "Cost Center: CC000326 PBS - Procurement & Business Services","Function: FN16300 General Administrative - Logistical Services". "Designated:DE00002330 Equipment Gifts - Equipment Gits - Private" does not allow worktag values: "Cost Center: CC000326 PBS - Procurement & Business Services","Function: FN16300 General Administrative - Logistical Services". "GTRI Charge Code:J1146.0M.08.05.0002 CWAN REFRESH (inactive)" does not allow worktag values: "Cost Center: CC000253 GTRI-SISD - Sensors and Intelligent Systems". "GTRI Charge Code:L1116.01.00.00.0001 OIT SERVICES" does not allow worktag values: "Cost Center: CC000239 GTRI - DDOPS - Operations".
Business Assets |  | GT | Run Missing Year 2 Equipment Asset Process and Confirm on the Ledger | Run process to retire equipment assets missing for 2 fiscal years - Financial Accounting team to review on the Ledger | Wednesday | 2023-07-05 | Complete | Frederick Trotter Tanisha Tigner Michael Barnwell Kelly MacArthur Meagan Fitzsimons
Payroll |  | GT | Deadline: Late Timesheets Due - Periods Prior to 6/10 | Deadline: Late Timesheets for pay periods ending prior to June 10 must be submitted via ServiceNow - Payroll | Wednesday | 2023-07-05 | Complete | Jerri Phillips | Deadline date
Business Assets |  | GT | Final Journal Entries to Business Asset Ledger Accounts | Final Journal Entries to Common Book for Business Asset Ledger Accounts | Thursday | 2023-07-06 | Complete | Frederick Trotter Regina Wilson Tanisha Tigner | 7/6/21: Should be completed today
Business Assets |  | GT | Reconcile Common book and Capital book balances for equipment for FY2023 | Reconcile Common Book and Capital Book balances for equipment for FY2023 NOTE: No JEs can be posted to GTPE, GTRI, G&C once they close | Thursday | 2023-07-06 | Complete | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur | 7/6/21- In progress and should be completed today
GTRI |  | GT | GTRI Accounting Close | Final close for GTRI Accounting (inlcudingQPOST&HPOST&Machine Shop) | Thursday | 2023-07-06 | Complete | Alice Fellabaum Aparna Mandiga April Howze Julie McCoy | * must be on-call for closing issues 7/7/21 - HPOST was posted this morning 7/9/21 - Last closing entry for Indirect funds will be today | 7/7/22 - QPS_20220630_01 GRI_20220630_01 GTI_20220624_01 GTI_20220630_03 GTRI has completed their close | 7/6/23: HPost Being entered into ONEUsg today, will be processed in Workday tomorrow 7/7. Qpost will post directly to workday today.
Financial Accounting |  | GT/ATHL | Review Books and Book Codes | Confirm Book Codes are correct for each Book | Thursday | 2023-07-06 | Complete | Maurena Maynor Amy Herron |  | Command: Book Code | 7/5/23: Duplicate of task: Ensure Workday Book Codes are aligned to the Correct Books from June 9th
GTRI |  | GT | Georgia Tech Applied Research Corp (GTARC) Gifts Close | Georgia Tech Applied Research Corp (GTARC) Gifts Close | Friday | 2023-07-07 | Complete | Alice Fellabaum April Howze Julie McCoy | * must be on-call for closing issues 7/7/21 - Working on ths today or tomorrow |  | Must wait for Hpost, will let teams know when to proceed. GTI_20230630_18
Financial Accounting |  | GT | Georgia Tech Foundation (GTF) Gifts Close | Georgia Tech Foundation (GTF) Gifts Close | Friday | 2023-07-07 | Complete | Jacob Jacobs Maurena Maynor Amy Herron |  |  | Must wait for Hpost, will let teams know when to proceed.
Grants |  | GT | Georgia Tech Research Corporation (GTRC) Gifts Close | Georgia Tech Research Corporation (GTRC) Gifts Close | Friday | 2023-07-07 | Complete | Josh Rosenberg Amy Zhang Doug Feller | * must be on-call for closing issues | GCA_20220630_01 | Must wait for Hpost, will let teams know when to proceed. GCA_20230630_06
Grants |  | GT | Grants and Contracts Accounting Close | Grants and Contracts Close | Friday | 2023-07-07 | Complete | Josh Rosenberg Amy Zhang | * must be on-call for closing issues | GSJ_20220630_06 ~ 08 | GSJ_20230630_01, GSJ_20230630_02
Grants |  | GT | GTPE & EI2 Indirect Allocation Journal | GTPE & EI2 Indirect Allocation Journal | Friday | 2023-07-07 | Complete | Amy Zhang Tony Wang Neli Tranakiev | Per Amy, G&C will tell Yongmei when it is ready to post (after Customer Accounts close), then she will actually post | 7/7/22 - FSM does not have to alter the allocations to post to FY22 | Must wait for Hpost, will let teams know when to proceed.
Grants |  | GT | GIT Revenue Correction | To correct GIT revenue and unbilled.Ledger account 954100: Grants Revenue/Offset Memo Account must be 0.00. | Friday | 2023-07-07 | Complete | Amy Zhang Tony Wang Neli Tranakiev Josh Rosenberg Chris Cho |  | GSJ_20220630_01 ~ 05 | Must wait for Hpost, will let teams know when to proceed. GSJ_20230630_03, GSJ_20230630_04,GSJ_20230630_05, 954100 account balance is 0
Financial Accounting |  | GT | Clear Bank Recon Items | Make JE's as needed to clear/correct recon items for both Operating and Receipts Clearing Bank accounts | Friday | 2023-07-07 | Complete | Tammy Putnal Leanne Sheffield | 7/6/21 - BW payroll verificiation on Bank 7/7/21: Waiting on a payroll file today or tomorrow | 7/8/22 - Leanne will let FSM team know by 4:30PM to close banking. If not, FSM will circle back with Leanne if no email.
Financial Accounting |  | GT | Banking Reconciliation - June | Banking Reconciliation for Month End Close (June) | Friday | 2023-07-07 | Complete | Tammy Putnal Leanne Sheffield |  | 7/8/22 - Leanne will let FSM team know by 4:30PM to close banking. If not, FSM will circle back with Leanne if no email ***Line above can be combined for FY23. | Must wait for Hpost, will let teams know when to proceed. 7//7/2023: Tammy mentioned this wil be complete Monday morning.
ERP |  | GT/ATHL | Quarterly Planned Maintenance ***Sandbox, Sandbox Preview and Impl | Tenant downtime - Friday 9 PM to Saturday 1 PM Eastern time | Friday | 2023-07-07 | Complete | David Adcock | Friday - Saturday
Financial Accounting |  | GT | Perkins Loan Reconciliation for FY2023 | Perkins Loan Reconciliation for FY2023 - Reconcile GL with ACS reports and move advances, repayments, cancellations etc to cumulative loan receivable. | Friday | 2023-07-07 | Complete | Curlyne Andrews Gloria Kobus Xin Mu | 7/9/2021 - Still in progress |  | 7/11/2023: Waiting on update.
Financial Accounting |  | GT | Review Journals posted to Sponsored Fund Codes (2xxxx) for Year End | Run "Find Journal Lines - CR" report to view sponsored JE charges posted after G&C close - Contact G&C or GTRI if journals are noted. | Friday | 2023-07-07 | Ongoing | Yongmei Zhang Tyler Dixon | Ongoing through Year-End
Financial Accounting |  | GT | Review of USG ChartField Changes | Review USG Chart of Accounts excel file for Ledger Account, Fund, Function and Class for changes and update Workday Financials | Friday | 2023-07-07 | Complete | Maurena Maynor Amy Herron Yongmei Zhang | 7/9/21 - No changes since Feb
Financial Accounting |  | GT | Compare Fund Balance | Compare fund balance in annual audit to fund balance in ACTUALS / CAPITAL / GAAP ledgers | Friday | 2023-07-07 | Complete | Maurena Maynor Amy Herron | 7/1/21: Not today; will need to change date for future | 7/11/22 - This will not effect YE close for FY22
PCard |  | GT | FY24- PCard Transaction Verification - 6/16-6/30 | Pcard Verifications (PCV) due for transactions posted to the bank btw 6/16-6/30 (FY24 Journal) | Friday | 2023-07-07 | Complete | Whittney Haynes |  | 7/5/2022 - Whittney wants to move this date to Monday July 11, 2022. There is a delay in BOA file. 7/11/22 - This JE is for FY23. This will not effect YE close for FY22 | Per Whittney Haynes on 7/6/23: They have enountered a Workday error that is preventing them from approving Pcard transactions. This will likely delay this deadline. Have spoken to Maurena who mentioned this will only affect her GAAP entry, and is okay long as it is complete before 7/12.
Various |  | GT | Allowance for Doutbtul Accounts | Create BOR entry YE-7c (ACTUALS ledger) - Notify FSM Team (gl.prodsupp@business.gatech.edu) that the entry has been created and the JE number | Friday | 2023-07-07 | Complete | Gloria Kobus Maurena Maynor |  | 7/7/22 - Per Gloria: Beginning in FY22, we are no longer making reserve entries. Bursar will need to notify FSM team (gl.prodsupp@business.gatech.edu) when this journal has been posted. For FY22 the JE is: BTS_20220630_03.
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-07-07 | Complete | David Adcock | Friday - Saturday
PCard |  | GT | Reconcile PCard Liability Account | FY23 - Reconciliation of PCard Liability Ledger Account | Sunday | 2023-07-09 | Complete | Whittney Haynes |  | 7/8/22 - AP to contact Whittney on status | Per Whittney Haynes on 7/6/23: They have enountered a Workday error that is preventing them from approving Pcard transactions. This will likely delay this deadline. Have spoken to Maurena who mentioned this will only affect her GAAP entry, and is okay long as it is complete before 7/12.
Financial Accounting |  | GT | Year-End Closing Review Checklist Due | Year-End Closing Review Checklist Due to Controller's Office. Submit only if significant items that require management review are disclosed. | Monday | 2023-07-10 | Complete | Christopher Drummond Amry Stanley
Financial Accounting |  | GT | Change Budget Reference Grants Allocation | Change the Budget Reference for the "G&C GIT Cost Reimbursable Indirect Revenue Allocation" Group set to BR24 | Monday | 2023-07-10 | Complete | Yongmei Zhang Tyler Dixon Serena Simpson Amy Herron |  | This is done when G&C is done for the Year
Budgets | BUD1 | GT/ATHL | Create Budget Templates for FY2024 | Create Budget Templates for FY2024: 1) Carryforward/oneBudget Combination 2)(Carryforward FY23/oneBudget FY24 Combo) Carryforward Structure (FY23 Carryforward) – Year will be prior yea Gift Budget Structure - 2 Templates 3) One for GF & GTF (FY24 GF & GTF) 4) One for GTRC (FY24 GTRC) 5) GTAA_Structure (FY24 GTAA Budget) 6) oneBudget/Sponsored Budget Authority Combined (FY24 oB/SBA Combined) 7) oneBudget Structure (FY24 Budget) 8) Sponsored Budget Authority (FY24 Sponsored Budget Authority) | Monday | 2023-07-10 | Complete | Richard Tanner Antinina Wilkerson |  | This step must be done before the other BUD steps (BUD2-BUD8)
Grants |  | GT/ATHL | Reporting Team to change Fiscal Year Covid Expense Reports updated to the new fiscal year FY24 | Verify with Deepthi and the Reporting Team that the new Fiscal Year FY24 for reports have been updated to default the new fiscal year. IBPA COVID Expenses - Program & Spend Category - CR IBPA COVID Expenses - Fund Source - CR IBPA COVID Expenses - Cost Center & Program - CR | Saturday | 2023-07-01 | Complete | Yongmei Zhang Tyler Dixon Nate Watkins Deepthi VenReddy |  | 6/29/2022 - This has been delayed to Saturday. Must wait for FSM team message to start. 6/30/2022 - Has to happen after hours 07/01/2022 | JIRA wkdya-8497, Financial & FDM reports are updated in GT7. Deepthi will update these reports in 07/01/2023 in PROD. Covid Expense reports Fiscal year field need be update the New fiscal year FY24. New Fiscal year has been updated after the new fiscal year is updated after 07.01.2023
|  | GT/ATHL | Reporting Team to change Fiscal Year Executive Revenue Dashboard - Tab Prompt new fiscal year and new budget structure ( FY24 oB/SBA Combined) | Verify with Deepthi and the Reporting Team that the new Fiscal Year and new budget structure (FY24 oB/SBA Combined). This has been done after Richard has loaded budget template for FY24. IBPA - BOR Summary Revenue Quarterly Report - GTCR IBPA - BOR GTRI Revenue Quarterly Report - GTCR IBPA - BOR RI Revenue Quarterly Report - GTCR IBPA - BOR EII Revenue Quarterly Report - GTCR | Monday | 2023-07-10 | Complete | Yongmei Zhang Tyler Dixon Nate Watkins Deepthi VenReddy |  |  | JIRA wkdya-8497, Financial & FDM reports are updated in GT7. Deepthi will update these reports in 07/01/2023 in PROD. Executive Revenue Dashboard - Tab Prompts.
Budgets | BUD4 | GT | EIB Budget Load for FY2024 - Georgia Tech "GTRC Gift" Budget Structure | EIB Budget Load for FY2024 - Georgia Tech "GTRC Gift" Budget Structure ---Calculation is Budget minus Actuals | Monday | 2023-07-10 | Complete | Amy Zhang Doug Feller Josh Rosenberg Yongmei Zhang Serena Simpson Tyler Dixon | 7/29/21 - Paul: GTRC is almost done and could possibly be put into Production tomorrow. | 7/11/22 - Per Doug this has been completed with the exception of 2 worktags (DE00016445 and DE000020698. Doug is working with Gift Managers to correct these. | @Tyler; Going forward Gift Budget Amendments/Expenses should post in FY24
Budgets | BUD5 | GT | EIB Budget Load for FY2024 - Georgia Tech "CarryForward" Budget Structure (for PY PO's) for Non-Sponsored Funds | Budget Load for FY2024 - CarryForward for Purchase Orders rolled forward into FY2024. ---FDM string should be pulled from roll forward POs and budget should match. ---PO Number should be entered in External Ref ID field. ---Non-Sponsored Funds Codes Only (not like 2xxxx), Exclude FD62000 (Custodial) ---Use"Build Carryforward Budgets"-CR | Monday | 2023-07-10 | Complete | Christopher Drummond Amry Stanley Yongmei Zhang Serena Simpson Tyler Dixon Amy Herron | WKDAY-2281 - can load early if ready
Budgets | BUD6 | GT | EIB Budget Load for FY2024 - Georgia Tech "oneBudget" Budget Structure - GT Operating Budget | EIB Budget Load for FY2024 - oneBudget - Budget Ref is BR24 | Monday | 2023-07-10 | Complete | Richard Tanner Kim Short Brian McRae | WKDAY-2281 - can load early if ready
Budgets | BUD7 | GT | EIB Budget Load for FY2024- Georgia Tech "Sponsored Budget Authority" Budget Structure | EIB Budget Load for FY2024 - Sponsored Budget Authority - Budget Ref is BR24 | Monday | 2023-07-10 | Complete | Richard Tanner Kim Short Brian McRae | WKDAY-2281 - can load early if ready
Payroll |  | GT | Deadline - Biweekly Timesheets for Period Ending 7/8 | Deadline for timesheets - Biweekly pay period ending 7/8 | Monday | 2023-07-10 | Complete | Jerri Phillips | No confirmation Needed
PCard |  | GT | PCard Transaction Load FY24 - 7/1 to 7/9 | PCard transactions that hit bank btw 7/1 to 7/9 loaded into Workday. Normal daily transaction loads resume. | Monday | 2023-07-10 | Complete | Whittney Haynes Mike McCoy Timothy Hughes Chhaya Amin |  |  | Per Whittney Haynes on 7/6/23: They have enountered a Workday error that is preventing them from approving Pcard transactions. This will likely delay this deadline. Have spoken to Maurena who mentioned this will only affect her GAAP entry, and is okay long as it is complete before 7/12.
Commitment Accounting | COMM2 | GT | Commitment Accounting Closed for FY2023 Year End | Commitment Closed for FY2023 Year End | Tuesday | 2023-07-11 | Complete | Terryl Barnes Jason Cole Anagha Sahasrabudhe Jana Wagner |  |  | BFR is apart of this as well as Hpost. BFR to post 7/10, Hpost to post 7/7. 7/10/23 - BFR to post on 7/11/23 due to USG delay
Financial Accounting | FINCLOSE1 | GT/ATHL | Final Close Processes for FY2023 Operating Ledger | Follow YearEndRunSheet | Tuesday | 2023-07-11 | Complete | Yongmei Zhang Tyler Dixon Serena Simpson Amy Herron |  | 7/8/22 - This will be completed on MONDAY | Delayed to 7/11/23 due to BFR journal posting delay
Financial Accounting |  | GT | Final Fringe Benefits (BFR) Journal Posted to the Ledger | Final Fringe Benefits (BFR) Journal Posted to the Ledger for FY2023 - Send Email to FinOps to post - If file has not be received contact Taylor Ferguson. This file will not be given until the 5th working day and will post on the 6th working day of the month. This journal does not affect Grants, GTRI or Gifts close. | Tuesday | 2023-07-11 | Complete | Kedrich Claiborne Jerri Phillips Yongmei Zhang Tyler Dixon | Can confirm via Find Journals - CR report in Workday | 7/7/22- Per Kedrich: Has not been completed yet. The process will not begin until Friday. If everything goes well, will be ready for posting Monday. Unfortunately we have to wait on OneUSG to provide the data to run the Ben Recon process. This will effect expense accoutns as well. | 7/5/230- Terryl spoke with Kedrick and this journal may not post till Monday 7/10/23. Kedrich: Due to shared services, this journal will not post till Monday 10th. This will be an issue every year. Lisa will not be able to complete her reconciliation until this journal is posted. 7/10/23 - BFR to post on 7/11/23 due to USG delay
Financial Accounting | FINCLOSE2 | GT/ATHL | Workday Financials Operating Ledger Closed for FY2023 | Workday Financials Operating Ledger Closed for FY2023 (GT Common Book: Closed GT Capital Book: Closed in Progress except for Journals and Assets) | Tuesday | 2023-07-11 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson Amy Herron |  | Capital: Close in progress (open for Assets and Journals) Common: Closed 7/8/22 - This will be completed on MONDAY | Delayed to 7/11/23 due to BFR journal posting delay
Financial Accounting |  | GT | Budget Office and Controller's Office Final Year End Closing Entries | Final Closing Entries for Controller's Office and Budget Office for FY2023 | Tuesday | 2023-07-11 | Complete | Amy Herron Maurena Maynor Jamie Fernandes Lisa Godfrey |  |  | Delayed to 7/11/23 due to BFR journal posting delay
Budgets |  | GT | Budget to Actuals Alignment | Align the actuals to the budget by Fund and Category for PS/NPS as mandated by BOR - This cannot happen until all material adjustments have been posted | Tuesday | 2023-07-11 | Complete | Lisa Godfrey Jamie Fernandes | 7/9/21 - Grants needs to be done before this step. |  | Delayed to 7/11/23 due to BFR journal posting delay
Budgets |  | GT | Create and Post Final Sponsored Budget Authority EIB File for FY2023 | Create and Post Final Sponsored Budget Authority File for FY2023 - Budget Ref is FY2023 | Tuesday | 2023-07-11 | Complete | Isabel Lynch Lisa Godfrey Antinina Wilkerson Nate Watkins | 7/9/21 - Grants needs to be done before this step. |  | Delayed to 7/11/23 due to BFR journal posting delay
Budgets |  | GT | Ensure BOR budget authority requested for all funds is greater than FY2023 estimated expenses | Ensure BOR budget authority requested for all funds is greater than FY2023 estimated expenses | Tuesday | 2023-07-11 | Complete | Lisa Godfrey Jamie Fernandes | 7/2/21: Posted on Wednesday and more up to the 9th. 7/9/21 - Need G&C to close before this step |  | Delayed to 7/11/23 due to BFR journal posting delay
Financial Accounting |  | GT | Trial Balance Blessed - Common Book | All FY2023 transactions for the Common Book have been posted. Controller's Office and Budget Office run Analysis of Fund Balance Report to confirm. | Tuesday | 2023-07-11 | Complete | Amy Herron Maurena Maynor Jamie Fernandes Lisa Godfrey |  |  | Delayed to 7/11/23 due to BFR journal posting delay
Financial Operations |  | GT | Process EIB file with oneUSG Obligations for FY2024 to the ledger | Load EIB file with oneUSG Obligations for FY2024 to the ledger | Tuesday | 2023-07-11 | Complete | Terryl Barnes Jeff Benenati Chhaya Amin |  |  | 7/11/2023 - Terryl will complete today after EDW refresh, does not affect FY23 close. This is a FY24 task
Budgets | BUD2 | ATHL | EIB Budget Load for FY2024 - Georgia Tech "Athletics" Budget Structure | EIB Budget Load for FY2024 - Georgia Tech "Athletics" Budget Structure ---Calculation is Budget minus Actuals | Tuesday | 2023-07-11 | Complete | Selinda Biggers Antinina Wilkerson Nate Watkins | WKDAY-2281 7/29/21 - Paul: Will circle back with Selinda. She is not ready | 7/11/22 - Per Selinda, she will not close yet. This can be TBD for now. | 7/11/2023 - Selinda is still working on this. To be done by next week. Per Selinda on 7/27 - ATHL aims to be complete Monday 7/31
Financial Accounting |  | GT | Review/Run - Close Ledger Year for COMMON Book Code for GT and Roll Forward Year-End Balances | Review/Run - Close Ledger Year for COMMON Book Code for GT and Roll Forward Year-End Balances - Add Accounts to Closing Rules ***Ledger Accounting Source - 342100 (Unallocated Net Asset - Current Year (Unrestricted) ***Ledger Account Target - 341100 Unallocated Net Asset - Prior Year (Unrestricted) | Tuesday | 2023-07-11 | Complete | Yongmei Zhang Tyler Dixon Serena Simpson Amy Herron |  |  | Delayed to 7/11/23 due to BFR journal posting delay
Commitment Accounting |  | GT | Generate Transactions and Provide Payroll Obligations (Encumbrances) EIB File to Workday/Financial Accounting for FY2024 | Generate Transactions and Provide Payroll Obligations (Encumbrances) EIB File to Workday/Financial Accounting for FY2024 | Tuesday | 2023-07-11 | Complete | Terryl Barnes Anagha Sahasrabudhe Jason Cole Richard Tanner |  |  | 7/11/2023: Will be today after the EDW refresh.
Business Assets | SEC07 | GT | CENTRAL - Asset Issue Event and Asset Transfers CLOSED for FY23 ADD BACK Custom Validation - Asset Issue Event, Asset Transfer Event (reviewing) | ***Add custom validation on Asset Registration and Asset Assign Accounting - "YE - Source not Manual Registration or Capital Project" to prevent "Business Assets Accountant - Equipment" from Registering Assets or Assigning Accounting. | Tuesday | 2023-07-11 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson Denise Hairston Frederick Trotter Tanisha Tigner Tray Mathis | Run this by Kelly and Amy | ATHL and Controllers office will be able to still register/transfer assets (Business Assets - Non Equipment Role is not removed which gives them this capability) | Delayed to 7/11/23 due to BFR journal posting delay
Business Assets | SEC07a | GT | CENTRAL - Assets Registration and Asset Assign Accounting CLOSED for FY23 REINSTATE Custom Validation added on Asset Registration Event (Covers Asset Assign Accounting) | ***Add Custom Valiation on Asset Registration - "YE - Source not Manual Registration or Capital Project" to prevent "Business Assets Accountant - Equipment" from Registering Assets (Covers Asset Accounting) | Tuesday | 2023-07-11 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson Denise Hairston Frederick Trotter Tanisha Tigner Tray Mathis | Run this by Kelly and Amy | ATHL and Controllers office will be able to still register/transfer assets (Business Assets - Non Equipment Role is not removed which gives them this capability) 7/8/22 - Per AH, Kelly said go ahead and add | Delayed to 7/11/23 due to BFR journal posting delay
SupplAccts |  | GT | Prepaid Spend Amortization | Review/test prepaid spend amortization to ensure that it can post transactions to BR24. The budget ref must be BR24 on these transactions. | Tuesday | 2023-07-11 | Complete | Yousaf Farhat Whitney Tate Daniel Stewart Amry Stanley Kelly MacArthur Laura Jamison |  |  | Notes from Carol Gibson 7/11/23: 1) Prepaid Expenses that reference a PO - Use Prepaid Spend Amortization process (BR will reference BR on PO - no JE needed) 2 - Prepaid Expenses that reference a SIR - Use JE to Debit Expense Ledger Account (ex. 727100) and Credit Prepaid Expense ledger Account (132101) (BR should be current year - FY24/BR24) -
Grants |  | GT | To clear 954100 account for entries missing Function in GAAP book. | Grants and Contracts will test the EIB in sandbox and then send the EIB to Controller office after G&C completed YE close. Controller office will upload the EIB. | Tuesday | 2023-07-11 | Complete | Amy Zhang Doug Feller Tony Wang Neli Tranakiev
Financial Accounting |  | GT | Custodial Entity Review for Year End | Review Custodial Entities for FY2023 and create JE for AFR (GAAP002) | Tuesday | 2023-07-11 | Complete | Christopher Drummond Amry Stanley
Financial Accounting |  | GT | Year-End Closing Review Checklist Review by Compliance Team Due | Year-End Closing Review Checklist Review by Compliance Team Due | Tuesday | 2023-07-11 | Complete | Christopher Drummond Amry Stanley
Integrations |  | GT | Process EIB file with oneUSG Payroll Obligations (Encumbrances) for FY2024 to the ledger | Process EIB file with oneUSG Payroll Obligations (Encumbrances) for FY2024 to the ledger | Tuesday | 2023-07-11 | Complete | Terryl Barnes Jeff Benenati Chhaya Amin | 7/9/21 - May happen this morning
Financial Accounting |  | GT | A/P Stops Processing Transactions at Lunch for Capital Book Postings | A/P will stop processing transactions for 30 minutes at lunchtime to allow Capital Book Operational Journals in Error to Post | Tuesday | 2023-07-11 | Complete | Laura Jamison & Denise Hairston | This will start the day after the Common Book Closes and will last until the Capital Book is Closed in late July.
Financial Accounting |  | GT | FinOps Delays Posting of GTAP Processing Until 5:30pm for Capital Book Postings | FinOps will delay processing GTAP transactions until 5:30pm to allow Capital Book Operational Journals in Error to Post | Tuesday | 2023-07-11 | Complete | Jeff Benenati & Denise Hairston | This will start the day after the Common Book Closes and will last until the Capital Book is Closed in late July.
Financial Accounting |  | GT | Asset Depreciation -June | Asset Depreciation for Month End Close (June) | Monday | 2023-07-12 | Complete | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur
Payroll |  | GT | Biweekly Pay Period End Date - 7/8 | Biweekly Pay Period End Date | Wednesday | 2023-07-12 | Complete | Jerri Phillips | No confirmation needed
Bursar |  | GT | Change Federal Work Study Driver Worktag | Change driver worktag for new FY after 1st BW Payroll (PE 07/08/2023) is entered: Bursar department is only creating new FWS worktag for new FY. Once they create the worktags and send to Terryl Barnes who is Dir-Commitment Accounting, Institute Budget Planning & Ad. Their part is done. Terryl will reach out Payroll office to make sure their side updates the new worktag to payroll system. | Wednesday | 2023-07-12 | Complete | Gloria Kobus Xin Mu Terryl Barnes
Payroll |  | GT | Biweekly Payroll Posted to Ledger - Period Ending 7/8 | BW payroll transactions from Pay Period Ending 7/8 posted to ledger | Wednesday | 2023-07-12 | Complete | Jerri Phillips Terryl Barnes |  |  | 7/14/23 - Terryl still resolving issues with OneUSG Commitment Accounting transactions and the first biweekly payroll to the Workday ledger.
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-07-14 | Complete | David Adcock | Friday - Saturday
Budgets | BUD3 | GT | EIB Budget Load for FY2024 - Georgia Tech "GTF Gift" and "Gifts (GF)" Budget Structure | EIB Budget Load for FY2024 - Georgia Tech "GTF " Budget Structure ---Calculation is Budget minus Actuals | Monday | 2023-07-17 | Complete | Maurena Maynor Amy Herron Yongmei Zhang Serena Simpson Tyler Dixon |  | 7/11/22 - Per Maurena, Budgets for gifts can not load until Robert finalizes his side. Maurena spoke with Lee about this. FSM team may want to push the date back to 7/18/22.
Security | SEC06o2 | GT/ATHL | CAMPUS - Budget Amendments for Gifts OPEN for FY24 ADD BACK Security for Budget Amendment Event | Add Back campus security roles from Business Process Policy Initiation Steps so users can enter transactions. (@ 9AM) | Monday | 2023-07-17 | Complete | Marvin Petty Maurena Maynor Doug Feller Josh Rosenberg | Roles: Cost Center Manager, Gift Manager, Grants Manager, Grants Budget Amendment Creator, Project Master BPs: Budget Amendment Event |  | This item is contingent on the carry-forward budget being complete. Per Maurena Maynor 7/10/23 - Delayed to 7/11/23 due to BFR journal posting delay. Wait for Controller's office to give go ahead. Per Maurena, she needs to put in the original budget. After she adds the original budget then we can give back access. 7/12/23 - Wait on Controller's office to give the word
Grants |  | GT | ASRs available electronically | ASRs available electronically | Monday | 2023-07-17 | Complete | Jonathon Jeffries
Business Assets |  | GT | Deadline - Auxiliary Work in Process - NonEQ | Deadline - Auxiliary Work in Process - NonEQ | Wednesday | 2023-07-19 | Complete | Brian Cochran Denise Hairston Sharon Ahmed |  | 07/20/2022 - This is still in progress. Kelly will update the task list once it's complete. Completed 07/27/22 | Sharon Ahmed should be added.
Business Assets |  | GT | Deadline - Facilities Work in Process - NonEQ | Deadline - Facilities Work in Process - NonEQ | Wednesday | 2023-07-19 | Complete | John Richardson Denise Hairston |  | 07/20/2022 - This is still in progress. Kelly will update the task list once it's complete. Completed 07/27/22
Business Assets |  | ATHL | Run Depreciation Processes for FY2023 - Equipment | Review and verify transactions on the Capital Book | Wednesday | 2023-07-19 | Complete | Selinda Biggers |  | 07/20/22 - Per Denise Hairston: This will not be completed today. This will be completed on or before Friday 22nd. | Per Selinda on 7/27 - ATHL aims to be complete Monday 7/31
Business Assets |  | GT/ATHL | Run Depreciation Processes for FY2023 - Non-Equipment | Review and verify transactions on the Capital Book | Wednesday | 2023-07-19 | Complete | Selinda Biggers Denise Hairston Avni Patel Regina Wilson Kelly MacArthur |  |  | 7/25/23 - GT assets team has completed their depreciaiton, ATHL still working on theirs. Per Selinda on 7/27 - ATHL aims to be complete Monday 7/31 10/5- ATHL still working on YE close
Business Assets | BA1 | GT | Final Analysis of Depreciation Calculations & Lease Payments | Analyze Depreciation Calculations & Lease Payments | Friday | 2023-07-21 | Complete | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur |  | 7/21/22-Per Kelly M. We will not close on Saturday. It will be possibly 27th. | 7/25/23 - Per Regina, Assets team is still working on this with plans to complete by tomorrow.
Business Assets | BA2 | GT | Review transactions and Post Final Closing Entries for Capital ledger | Review transactions and Post Final Closing Entries for Capital ledger | Friday | 2023-07-21 | Complete | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur |  | 7/21/22-Per Kelly M. We will not close on Saturday. It will be possibly 27th. | 7/25/23 - Per Regina, Assets team is still working on this with plans to complete by tomorrow.
Business Assets | BA3 | GT | Final Recon of Asset Additions, Adjustments & Retirements | Final Recon of Asset Additions, Adjustments & Retirements | Friday | 2023-07-21 | Complete | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur |  | 7/21/22-Per Kelly M. We will not close on Saturday. It will be possibly 27th. | 7/25/23 - Per Regina, Assets team is still working on this with plans to complete by tomorrow.
Business Assets | BA4 | GT | Review Ledger and Confirm Business Assets Closed for FY2023 | Review Ledger and Confirm Business Assets Closed for FY2023 | Friday | 2023-07-21 | Complete | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur |  | 7/21/22-Per Kelly M. We will not close on Saturday. It will be possibly 27th. | 7/25/23 - Per Regina, Assets team is still working on this with plans to complete by tomorrow.
Property Control |  | GT | Property Control needs to review and approve any accounting adjustments that are sitting in the que for the new fiscal year. (FY24-JUL) | After we close Capital, Property control needs to approve any accounting adjustments that are sitting in the queue for FY24-JUL | Friday | 2023-07-21 | Complete | Frederick Trotter Tanisha Tigner Kelly MacArthur
ERP |  | GT/ATHL | Quarterly Planned Maintenance - PROD | Tenant downtime: Saturday 2 AM to Saturday 2 PM Eastern Time | Saturday | 2023-07-22 | Complete | David Adcock
Financial Accounting |  | GT | GSFIC Reconciliation | Reconcile spending on GSFIC projects and reimbursements from GSFIC to GSFIC reports. Prepare GAAP JE to set-up Accounts Receivable. | Saturday | 2023-07-22 | Complete | Kelly MacArthur Julie Alvoid Amy Herron | 7/30/21- Not Completed |  | 8/1/23: Per Kelly, her team is working on this this week.
Financial Accounting | BA5 | GT | Review/Run - Close Ledger Year for Capital Book Code for GT and Roll Forward Year-End Balances | Review/Run - Close Ledger Year for Capital Book Code for GT and Roll Forward Year-End Balances - Add Budget Ref to Closing Rules - Confirm with Capital Assets Accounting Team | Saturday | 2023-07-22 | Complete | Yongmei Zhang Tyler Dixon Serena Simpson Denise Hairston Frederick Trotter Tanisha Tigner Tray Mathis |  | 7/21/22-Per Kelly M. We will not close on Saturday. It will be possibly 27th. | 7/21/2023 - Per Kelly we will not close yet, aiming for Wednesday 7/26/2023.
Business Assets |  | GT | Provide List of Assets for the Audit | Tie CAPITAL ledger asset totals to detail listing of asset ID's | Tuesday | 2023-07-25 | Complete | Denise Hairston Avni Patel Regina Wilson Kelly MacArthur |  | 8/02/22 - Per Kelly. This task is in progress, will provide the list to auditors by the deadline in August. Also like to discuss why this in the FSM checklist later.
SupplAccts |  | GT | Clear Prepaids in New FY | Clear Prepaids in New FY | Tuesday | 2023-07-25 | Complete | Yousaf Farhat Laura Jamison Daniel Stewart |  | 7/27/22 - Per Abbie. It is still in progress. | 7/27/23 - Per Yousaf he is still working on prepaid journals (amortization) expected to be done today/tomorrow.
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-07-28 | Complete | David Adcock | Friday - Saturday
Financial Accounting |  | GT | Final Interest Income Allocation | Post Final Interest Income Allocation | Friday | 2023-07-28 | Complete | Maurena Maynor Leanne Sheffield Controller's Office | 7/6/21 - Waiting on all data; Investment account JE will be completed possibly today 7/7/21 - Entry may not be done today 7/8/21 - Entry in GAAP; middle of july
Payroll |  | GT | Compensated Absences | Report for additional leave liability that lists all leave earned, taken and leave balance by employee multiplied by hourly rate. | Tuesday | 2023-08-01 | Complete | Jerri Phillips Amy Herron Maurena Maynor
Business Assets | SEC08 | GT | CENTRAL - Asset Issue Event and Asset Transfers OPEN for FY2024 - Property Control & Surplus REMOVE Custom Validation - Asset Issue Event, Asset Transfer Event | Business Assets closed from 6pm on 7/10 until 9am on 8/1 - Remove Property Control and Surplus Security Groups from Asset Transaction Business Process Policy Initiation Steps so units cannot enter transactions. Remove custom validation on Asset Registration and Asset Assign Accounting - "YE - Source not Manual Registration or Capital Project" to prevent "Business Assets Accountant - Equipment" from Registering Assets or Assigning Accounting. (@ 5PM) | Tuesday | 2023-08-01 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson Denise Hairston Frederick Trotter Tanisha Tigner Tray Mathis
Business Assets | SEC08a | GT | CENTRAL - Assets Registration and Asset Assign Accounting OPEN for FY24 REMOVE CUSTOM VALIDATION for Asset Registration Event and Asset Assign Accounting | Business Assets closed from 6pm on 7/10 until 9am on 8/1 - Remove Property Control and Surplus Security Groups from Asset Transaction Business Process Policy Initiation Steps so units cannot enter transactions. Remove custom validation on Asset Registration and Asset Assign Accounting - "YE - Source not Manual Registration or Capital Project" to prevent "Business Assets Accountant - Equipment" from Registering Assets or Assigning Accounting. (@ 5PM) | Tuesday | 2023-08-01 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson Denise Hairston Frederick Trotter Tanisha Tigner Tray Mathis
Security | SEC08b | GT/ATHL | Asset Issue Event and Asset Transfers Open for FY2024 - Campus (Asset Issue Event, Asset Transfer Event) | Business Assets closed for Campus from 6pm on 6/21 until 9am on 8/1 - Add back Campus Asset Security Groups from Asset Transaction Business Process Policy Initiation Steps so campus can enter transactions. (@ 9AM) | Tuesday | 2023-08-01 | Complete | Marvin Petty Yongmei Zhang Tyler Dixon Serena Simpson Denise Hairston Regina Wilson Avni Patel Kelly MacArthur Frederick Trotter Tanisha Tigner | Note: Email needs to be sent out to campus in AM | Roles: Business Asset Tracking Specialist BPs: Asset Issue Event; Asset Transfer Event
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 10AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-08-04 | Complete | David Adcock | Friday - Saturday
Financial Accounting |  | GT | Review Year-End Accruals | Review Year-End Accruals - (A/P Accrual, Contracts Payable, Retainage Payable) | Friday | 2023-08-04 | Complete | Maurena Maynor Amy Herron Amry Stanley
ERP |  | GT/ATHL | Monthly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 9AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-08-11 | Complete | David Adcock | Friday - Saturday
Payroll |  | GT | Continuous Audit Report of Payroll | Provide Continuous Audit Report of Payroll - Dates will be confirmed at BOR Workshop | Monday | 2023-08-14 | Ongoing | Jerri Philips Kedrich Claiborne Controller's Office Maurena Maynor
SupplAccts |  | GT | Continuous Audit Report of Travel | Provide Continuous Audit Report of Travel - Dates will be confirmed at BOR Workshop | Monday | 2023-08-14 | Ongoing | Laura Jamison Michael Barnwell Liliana Blettler Daniel Stewart
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-08-18 | Complete | David Adcock | Friday - Saturday
ERP |  | GT/ATHL | Weekly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 5AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-08-25 | Complete | David Adcock | Friday - Saturday
Grants |  | GT | Certified ASRs due to Grants and Contracts | Certified ASRs due to Grants and Contracts | Thursday | 2023-08-31 | Complete | Jonathon Jeffries
ERP |  | GT/ATHL | Monthly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 9AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-09-15 | Complete | David Adcock | Friday - Saturday
ERP |  | GT/ATHL | Quarterly Planned Maintenance ***Sandbox, Sandbox Preview and Impl | Tenant downtime - Friday 9 PM to Saturday 1 PM Eastern time | Friday | 2023-10-06 | Complete | David Adcock | Friday - Saturday
SupplAccts |  | GT | Continuous Audit Report of Payment & Obligations, and TIGA P-card | Provide Continuous Audit Report of Payment and Obligations, and TIGA P-Card | Saturday | 2023-10-14 | Ongoing | Laura Jamison Michael Barnwell Whittney Haynes Daniel Stewart
ERP |  | GT/ATHL | Quarterly Planned Maintenance - PROD | Tenant downtime: Saturday 2 AM to Saturday 2 PM Eastern Time | Saturday | 2023-10-20 | Complete | David Adcock
Financial Accounting |  | GT | Deadline for Year End President's Discretionary Endowment (PDE) | Deadline to officially report final year end PDE | Monday | 2023-10-31 | Complete | Maurena Maynor Amy Herron Jim Pierce Lisa Godfrey | 7/9/21 - No funds from PDE will be used for FY21 Closeout; 07/19/22 - This entry is not completed until the BCR is finalized with the audit.
Financial Accounting |  | GT | Transfer President's Discretionary Endowment (PDE) | Transfer from PDE - Work with Budget Office | Wednesday | 2023-11-01 | Complete | Lisa Godfrey Maurena Maynor | Did not have to do this year
Business Assets | BA6 | ATHL | Final Analysis of Depreciation Calculations & Lease Payments | Analyze Depreciation Calculations & Lease Payments | Friday | 2023-11-17 | Complete | Selinda Biggers | 7/29/21 - Still waiting on Selinda
Business Assets | BA7 | ATHL | Review transactions and Post Final Closing Entries for Capital ledger | Review transactions and Post Final Closing Entries for Capital ledger | Friday | 2023-11-17 | Complete | Selinda Biggers | 7/29/21 - Still waiting on Selinda
Business Assets | BA8 | ATHL | Review Ledger and Confirm Business Assets Closed for FY2023 | Review Ledger and Confirm Business Assets Closed for FY2023 | Friday | 2023-11-17 | Complete | Selinda Biggers
Financial Accounting | BA9 | ATHL | Review/Run - Close Ledger Year for Capital Book Code for ATHL and Roll Forward Year-End Balances | Review/Run - Close Ledger Year for Capital Book Code for ATHL and Roll Forward Year-End Balances - Add Budget Ref to Closing Rules - Confirm with Capital Assets Accounting Team | Friday | 2023-11-17 | Complete | Yongmei Zhang Tyler Dixon Serena Simpson | 7/29/21 - Still waiting on Selinda
Financial Accounting |  | ATHL | GTAA Final Closing Journal Entries (Common Book) | Journals posted, corrections posted, etc. | Friday | 2023-11-17 | Complete | Selinda Biggers Tia Randolph Tyler Dixon Yongmei Zhang Serema Simpson | 7/14/21 - Possible Friday 7/29/21 - Still waiting on Selinda
Financial Accounting |  | ATHL | Update Ledger Period Status to Close Operational Accounting for FY2023 for ATHL | Mass Update Ledger Period Status Must happen after final Journals from campus | Friday | 2023-11-17 | Complete | Tyler Dixon Yongmei Zhang Serena Simpson | 7/14/21 - Possible Friday 7/29/21 - Still waiting on Selinda
ERP |  | GT/ATHL | Monthly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 9AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-11-17 | Complete | David Adcock | Friday - Saturday
ERP |  | GT/ATHL | Monthly Planned Maintenance - All Tenants | Tenant Downtime ***PROD - Saturday 2 AM to Saturday 9AM Eastern Time. ***Sandbox, Sandbox Preview and Impl - Friday 9 PM to Saturday 9 AM Eastern Time. | Friday | 2023-12-08 | Complete | David Adcock | Friday - Saturday
Financial Accounting |  | GT/ATHL | Review/Run - Close Ledger Year for GAAP Book Code for FY2023 for GT and ATHL and Roll Forward Beginning Balances | Close GAAP Ledger for FY2023 and Roll Forward Beginning Balances- FSM closes GAAP ledgers after confirmation from Maurena Maynor (GT) and Selinda Biggers (ATHL) | Monday | 2024-01-09 | Complete | Maurena Maynor Selinda Biggers Yongmei Zhang Tyler Dixon Serena Simpson |  | 1.9.23 - Per Maurena ATHL does not use GAAP
Financial Accounting |  | GT | Review/Run - Close Ledger Year for BCR Book Code for FY2023 for GT and Roll Forward Beginning Balances | Close BCR Ledger for FY2023 and Roll Forward Beginning Balances- FSM closes BCRP ledgers after confirmation from Maurena Maynor (GT) | Monday | 2024-01-09 |  | Maurena Maynor Selinda Biggers Yongmei Zhang Tyler Dixon Serena Simpson |  | *Per Maurena 1/30/23 - Proceed with closing BCR without a roll forward